## Use Case
UseCase >> ATM >> Withdraw
UseCase ID | UseCase Name | Actor | Goal | Pre-Condition | Flow/Path | Step | Post-Condition
UseCase_ATM_Withdraw | To withdraw money | Primary Actor: User | User Goal | ATM Mechine must be working | 1) Normal/Basic Path | 1. Insert ATM Card | Collect cash and ATM Card.
|  | Secondary Actor: ATM Card |  | Server must be working |  | 2. Select Language | Collect Receipt if we enter YES for the receipt.
|  |  |  | Cash must be available |  | 3. Select service->Withdraw | System should display available balance.
|  |  |  | ATM card must be vaild |  | 4. Enter ATM Pin | Enter EXIT if we don't want to continue.
|  |  |  | Balance must be available in account |  | 5. Select Account type
|  |  |  | ATM pin must be correct |  | 6. Enter Amount
|  |  |  | User must be registered user |  | 7. Re-enter Amount
|  |  |  | Balance must be available in ATM |  | 8. Select Denomination
9. Enter Yes/No for Print
[5 empty] | 2) Alternate Path: Cardless | 1. Select Cardless option | Collect cash.
[6 empty] | 2. Enter phone no./Bank account no. | Collect Receipt if we enter YES for the receipt.
[6 empty] | 3. Enter OTP | System should display available balance.
[6 empty] | 4. Account Verification | Enter EXIT if we don't want to continue.
5. Select Service->Withdraw
6. Select Account type
7. Enter Amount
8. Re-enter Amount
9. Select Denomination
10. Enter Yes/No for Print
[5 empty] | 3) Exceptional Path | 1. Withdraw Money more than 10000 Rupee. | Please re-start the transaction.
[6 empty] | 2. Using OTP Generate option. | Enter EXIT if we don’t want to continue.
3. If OTP is not Received.
4. ATM Pop Up message to check your Registered Mobile no. and Email ID.
5. User can request for an OTP to be re-sent to you up to maximum of Five times.
6. If you have exhausted the no. of attempts.
[5 empty] | IV) Error Path | 1. Inserting an Expired card. | Remove your card.
2. Entering an amount greater than the per day limit.
3. Entering an amount greater than the per transaction limit.
4. Entering an amount greater than the available balance in the account.
5. ATM Validates the PIN for the Card.
6. If PIN is incorrect, Re-enter your PIN.
7. User will get three attempts.
8. If all three attempts were wrong.
9. ATM will provide error message.

## Test Plan
Test Plan
Sr. No. | Parameters | Description | Column1 | Column2 | Column3 | Column4
Sr. No. | Parameter | Description
1 | TestPlanID | BloodBankToday_1.1_MTP_1.1
2 | References | BRS SRS Project plan Design Plan(optional) Development plan Configuration Management plan
3 | Introduction | In today's fast-paced world, medical emergencies can strike at any moment, leaving individuals in urgent need of blood transfusions. The availability of safe and compatible blood becomes crucial in such situations, and that's where the Blood Bank Today application comes into play. Blood Bank Today is a cutting-edge mobile application designed to bridge the gap between blood donors and recipients, ensuring a seamless and efficient blood transfusion process. Features: Donor Registration: Blood Bank Today allows potential donors to create their profiles, providing essential information such as blood type, location, and availability. Real-Time Blood Requests: Recipients in need of blood can post urgent requests on the application. Blood Bank Locator: Blood Bank Today includes a comprehensive database of local blood banks, along with their contact information, operating hours, and directions. Blood Donation History: Donors can access their personal blood donation history within the application. Community Engagement: Blood Bank Today fosters a sense of community by enabling donors and recipients to connect with each other through interactive forums, support groups, and blood donation events.
4 | Test Items | 1. Registration 2. Login 3. Find Blood 4. Request Blood 5. Blood Bank 6. Blogs 7. causes 8. Event 9. News 10. Videos 11. More 12. Donate us 13. Dashboard 14. My Messages 15. Edit Profile.
5 | Features to be Tested | 1. Registration 2. Login 3. Find Blood 4. Request Blood 5. Blood Bank 6. Blogs 7. causes 8. Event 9. News 10. Donate us 11. My Messages 12. Edit Profile.
6 | Features not to be Tested | 1. Videos 2. More 3. Dashboard
7 | Approach | Black Box Testing using (SDLC)WaterFall Model Methodalogy
8 | Item pass/Fail Criteria | NA
9 | Test Deliverable | 1. TestPlan 2. TestCases 3.Test Scenario 4. Defect Report
10 | Suspend, Resume Criteria | 1. When Showstopper defects arrive(Blocker defect) 2. Built is not received from development team 3. New change request received from the client.
11 | Environment Needs | I) OS Configuration 1. Device name : DESKTOP-KQ5EA4B 2. Processor : Intel(R) Core(TM) i3-5005U CPU @ 2.00GHz 2.00 GHz 3. Installed RAM : 4.00 GB 4. Device ID : 5ACB7833-4473-4C1A-91BD-9B16E5F8E416 5. Product ID : 00331-10000-00001-AA590 6. System type : 64-bit operating system, x64-based processor 7. Pen and touch : No pen or touch input is available for this display II) Browser: Google Chorme, Mozilla FireFox III) Tools: JMeter(Performance Testing tool), JIRA(Bug Tracking)
12 | Roles and Responsibilities | Sr. No. | Roles | Responsibilities
|  | 1 | Test Lead | Preparing Test Plan and Controlling On-going Activities
|  | 2 | Senior Tester | Analysing BRS, SRS Designing Test Scenarios Designing Test Cases
|  | 3 | Junior Tester | Checking Environment setup Executing the Testcases Preparing the Defect report Performing Re-testing
13 | Staffing and Training needs | Training is provided on JMeter and JIRA
14 | Schedule | Sr. No. | Roles | Responsibilities | Start Date | End Date
|  | 1 | Test Lead | Preparing Test Plan and Controlling On-going Activities | 2023-06-20 | 2023-06-21
|  | 2 | Senior Tester | Analysing BRS, SRS Designing Test Scenarios Designing Test Cases | 2023-06-21
|  | 3 | Junior Tester | Checking Environment setup Executing the Testcases Preparing the Defect report Performing Re-testing
15 | Software Risk Issue | 1. Design Plan Recieved but difficult to understand 2. If Government rule is changed for Example, changing the rates in the GST
16 | Risk and Contingency(Backup Plan) | 1. Environment Setup is not ready 2. Training is not provided 3. Not Proper follow up taken from team
17 | Approvals | Project Manager Name: Signature:

## Test Scenario
Test Scenario >> BLOOD BANK TODAY
Test Scenario_ ID | Test Scenario Name | Objectives | Pre-Conditions | Pre-Conditions
TS_Registration_001 | Registration | To check the Functionalities of Registration Module. | 1. System must be working. | 1.1 To check the Functionalities of Registration Module with Valid data.
|  |  | 2. Internet must be Available. | 1.2 To check the Functionalities of Registration Module with Invalid data.
|  |  | 3. Web Browser must be working. | 1.3 To check the Functionalities of Registration Module with Valid and Invalid data.
|  |  | 4. URL must be working. | 1.4 To check the Functionalities of Registration Module with Blank data.
|  |  | 5. Registration button must be clickable. | 1.5 To check the Functionalities of Registration Module with Mandatory data.
1.6 To check the Functionalities of Registration Module with Optionl data.
1.7 To check the Functionalities of Registration Module with already registered account.
TS_Login_002 | Login | To check the Functionalities of Login Module. | 1. System must be working. | 2.1 To check the Functionalities of Login Module with Valid data.
|  |  | 2. Internet must be Available. | 2.2 To check the Functionalities of Login Module with Invalid data.
|  |  | 3. Web Browser must be working. | 2.3 To check the Functionalities of Login Module with Valid and Invalid data.
|  |  | 4. URL must be working. | 2.4 To check the Functionalities of Login Module with Blank data.
|  |  | 5. Login button must be clickable. | 2.5 To check the Functionalities of Login Module with Autofill.
2.6 To check the Functionalities of Login Module with Forgot your password with Member ID
2.7 To check the Functionalities of Login Module with Forgot your password with Login ID
2.8 To check the Functionalities of Login Module with Forget your password with Email ID
2.9 To check the Functionalities of Login Module with Forgot your password with Mobile No
2.10 To check the Functionalities of Login Module with Sign in with Facebook.
2.11 To check the Functionalities of Login Module with Sign up now.
2.12 To check the Functionalities of Login Module with Back to Website.
2.13 To check the Functionalities of Login Module with without Registration.
TS_Find Blood_003 | Find Blood | To check the Functionalities of Find Blood Module. | 1. System must be working. | 3.1 To check the Functionalities of Find Blood Module with Blood Group
|  |  | 2. Internet must be Available. | 3.2 To check the Functionalities of Find Blood Module with Blood Group and State.
|  |  | 3. Web Browser must be working. | 3.3 To check the Functionalities of Find Blood Module with Blood Group, State and District.
|  |  | 4. URL must be working. | 3.4 To check the Functionalities of Find Blood Module with Blood Group, State, District and Tehsil.
|  |  | 5. Find Blood button must be Clickable. | 3.5 To check the Functionalities of Find Blood Module with empty fields.
TS_RequestBlood_004 | Request Blood | To check the Functionalities of Request Blood Module. | 1. System must be working. | 4.1 To check the Functionalities of Request Blood Module with Valid data.
|  |  | 2. Internet must be Available. | 4.2 To check the Functionalities of Request Blood Module with Invalid data.
|  |  | 3. Web Browser must be working. | 4.3 To check the Functionalities of Request Blood Module with Valid and Invalid data.
|  |  | 4. URL must be working. | 4.4 To check the Functionalities of Request Blood Module with Blank data.
|  |  | 5. Request Blood button must be Clickable. | 4.5 To check the Functionalities of Request Blood Module with Mandatory data.
4.6 To check the Functionalities of Request Blood Module with Optional data.
4.7 To check the Functionalities of Request Blood Module with Recent Donor Join.
TS_BloodBank_005 | Blood Bank | To check the Functionalities of Blood Bank Module. | 1. System must be working. | 5.1 To check the Functionalities of Blood Bank Module with State.
|  |  | 2. Internet must be Available. | 5.2 To check the Functionalities of Blood Bank Module with State and District.
|  |  | 3. Web Browser must be working. | 5.3 To check the Functionalities of Blood Bank Module with empty fields
4. URL must be working.
5. Blood Bank button must be Clickable.
TS_Blogs_006 | Blogs | To check the Functionalities of Blogs Module. | 1. System must be working. | 6.1 To check the Functionalities of Blogs Module with Hyperlink i.e. By Blood Bank today.
|  |  | 2. Internet must be Available. | 6.2 To check the Functionalities of Blogs Module with Facebook Share.
|  |  | 3. Web Browser must be working. | 6.3 To check the Functionalities of Blogs Module with Whatsapp Share.
|  |  | 4. URL must be working. | 6.4 To check the Functionalities of Blogs Module with Read More.
|  |  | 5. Blogs button must be Clickable. | 6.5 To check the Functionalities of Blogs Module with Reetack.
6.6 To check the Functionalities of Blogs Module with Web Solution Company Hyperlink.
6.7 To check the Functionalities of Blogs Module with Visit Icon.
6.8 To check the Functionalities of Blogs Module with Share Icon.
TS_Causes_007 | Causes | To check the Functionalities of Causes Module. | 1. System must be working. | 7.1 To check the Functionalities of Causes Module with Facebook Share.
|  |  | 2. Internet must be Available. | 7.2 To check the Functionalities of Causes Module with Whatsapp Share.
|  |  | 3. Web Browser must be working. | 7.3 To check the Functionalities of Causes Module with Donate Now.
|  |  | 4. URL must be working. | 7.4 To check the Functionalities of Causes Module with More Detail.
|  |  | 5. Causes button must be Clickable. | 7.5 To check the Functionalities of Causes Module with Visit Also.
TS_Events_008 | Events | To check the Functionalities of Events Module. | 1. System must be working. | 8.1 To check the Functionalities of Events Module with Facebook Share.
|  |  | 2. Internet must be Available. | 8.2 To check the Functionalities of Events Module with Whatsapp Share.
|  |  | 3. Web Browser must be working. | 8.3 To check the Functionalities of Events Module with Read More.
|  |  | 4. URL must be working. | 8.4 To check the Functionalities of Events Module with Visit Also.
|  |  | 5. Events button must be Clickable. | 8.5 To check the Functionalities of Events Module with Hyperlink i.e By Jayant Bansal.
TS_News_009 | News | To check the Functionalities of News Module. | 1. System must be working. | 9.1 To check the Functionalities of News Module with Facebook Share.
|  |  | 2. Internet must be Available. | 9.2 To check the Functionalities of News Module with Hyperlink i.e By Lakhvinder Singh
|  |  | 3. Web Browser must be working. | 9.3 To check the Functionalities of News Module with Whatsapp Share.
|  |  | 4. URL must be working. | 9.4 To check the Functionalities of News Module with Read More.
|  |  | 5. News button must be Clickable. | 9.5 To check the Functionalities of News Module with Visit Also.
TS_DonateUS_0010 | Donate Us | To check the Functionalities of Donate Us Module. | 1. System must be working. | 10.1 To check the Functionalities of Donate Us Module with QR Code.
|  |  | 2. Internet must be Available. | 10.2 To check the Functionalities of Donate Us Module with Mobile number
|  |  | 3. Web Browser must be working. | 10.3 To check the Functionalities of Donate Us Module with Displayed amount.
|  |  | 4. URL must be working. | 10.4 To check the Functionalities of Donate Us Module with Entering the amount Manually.
|  |  | 5. Donate us button must be Clickable. | 10.5 To check the Functionalities of Donate Us Module with Valid data.
10.6 To check the Functionalities of Donate Us Module with Invalid data.
10.7 To check the Functionalities of Donate Us Module with Valid and Invalid data.
10.8 To check the Functionalities of Donate Us Module with Blank data.
10.9 To check the Functionalities of Donate Us Module with Mandatory data.
10.10 To check the Functionalities of Donate Us Module with Optionl data.
10.12 To check the Functionalities of Donate Us Module with Recent Donor Join.
10.13 To check the Functionalities of Donate Us Module with Scrolling Arrow.
TS_My Message_011 | My Message | To check the Functionalities of My Message Module. | 1. System must be working. | 11.1 To check the Functionalities of My Message Module with three line which is present at the top left side.
|  |  | 2. Internet must be Available. | 11.2 To check the Functionalities of My Message Module with Reetack.
|  |  | 3. Web Browser must be working. | 11.3 To check the Functionalities of My Message Module with Back To Website.
|  |  | 4. URL must be working. | 11.4 To check the Functionalities of My Message Module with Your id: .
|  |  | 5. My Message button must be Clickable. | 11.5 To check the Functionalities of My Message Module with full name of the user which is present at the top right side .
11.6 To check the Functionalities of My Message Module with Settings Icon.
11.7 To check the Functionalities of My Message Module with Add Pages.
11.8 To check the Functionalities of My Message Module with Send Message.
11.9 To check the Functionalities of My Message Module with Search.
TS_Edit Profile_012 | Edit Profile | To check the Functionalities of Edit Profile Module. | 1. System must be working. | 12.1 To check the Functionalities of Edit Profile Module with Add Blood donation report.
|  |  | 2. Internet must be Available. | 12.2 To check the Functionalities of Edit Profile Module with Copy link.
|  |  | 3. Web Browser must be working. | 12.3 To check the Functionalities of Edit Profile Module with Facebook Share.
|  |  | 4. URL must be working. | 12.4 To check the Functionalities of Edit Profile Module with Whatsaap Share.
|  |  | 5. Edit Profile button must be Clickable. | 12.5 To check the Functionalities of Edit Profile Module with Copy for Profile ID.
12.6 To check the Functionalities of Edit Profile Module with Image.
12.7 To check the Functionalities of Edit Profile Module with Edit.
12.8 To check the Functionalities of Edit Profile Module with Save.
12.9 To check the Functionalities of Edit Profile Module with Edit your Email id.
12.10 To check the Functionalities of Edit Profile Module with Enter Email id.

## Test Case
Test Case
TestCase ID | Objectives | Pre-Condition | Step | Step Description | Test Data | Expected Result | Actual Result | Status |  |  | Remark | Defect
TS_01_TC_01 | To check the Functionalities of Registration Module with Valid data. | 1. System must be working. | 1 | Enter URL | https://bloodbanktoday.com/ | User should able to do registeration with Valid data. | User is able to register with Valid data but OTP is not working. Which is asking by the system for account verfication after clicking on Submit button. | Partially Failed. |  |  | After clicking on submit button system asking for OTP which user recevied on Dashboard rather than registered mobile number and in the Contact Information the spelling of Tehsil is incorrect it is written as 'Tehasil'. | OTP - Wrong fuctional defect. Tehasil - Non Fuctional Defect.
|  | 2. Internet must be Available. | 2 | Click on Registration Button. | Click
|  | 3. Web Browser must be working. | 3 | Enter Full Name | Pradeep
|  | 4. URL must be working. | 4 | Enter Email | Pradeep33reigns@gmail.com
|  | 5. Registration button must be clickable. | 5 | Enter Mobile Number | 7395835653
|  |  | 6 | Create Password | Pradeep@001
|  |  | 7 | Select BloodGroup | O+
|  |  | 8 | Select Gender | Male
|  |  | 9 | Select DOB | 2000-02-29
|  |  | 10 | Select Weight | 70
|  |  | 11 | Select Last Donation Date | 2023-11-03
|  |  | 12 | Select Yes/No for Show Mobile | Yes
|  |  | 13 | Select Yes/No for SMS Alert | Yes
|  |  | 14 | Enter Pin/Zip code | 641109
|  |  | 15 | Select State | TamilNadu
|  |  | 16 | Select District | Coimbatore
|  |  | 17 | Select Tehsil | Thondamuthur
|  |  | 18 | Enter City or Village | Devarayapuram
|  |  | 19 | Accept Terms & Conditions | Tick
|  |  | 20 | Click on Submit Buttom | Submit
|  |  | 21 | Enter OTP | OTP
TS_01_TC_02 | To check the Functionalities of Registration Module with Invalid data. | 1. System must be working. | 1 | Enter URL | https://bloodbanktoday.com/ | User should not get register with Invalid data. | User is able to registeration with Invalid data | Failed. |  |  | Fields like Full Name City should accept alphabets but in actual it is taking alphanumeric , Email is taking with wrong domain, Mobile no taking more than 3 digit. | Wrong Functional Defect.
|  | 2. Internet must be Available. | 2 | Click on Registration Button. | Click
|  | 3. Web Browser must be working. | 3 | Enter Full Name | Pradeep 123
|  | 4. URL must be working. | 4 | Enter Email | Pradeep123@gmail.com
|  | 5. Registration button must be clickable. | 5 | Enter Mobile Number | 73958356537
|  |  | 6 | Create Password | loook
|  |  | 7 | Select BloodGroup | O+
|  |  | 8 | Select Gender | Male
|  |  | 9 | Select DOB | 2000-02-29
|  |  | 10 | Select Weight | 610
|  |  | 11 | Select Last Donation Date | 2023-11-03
|  |  | 12 | Select Yes/No for Show Mobile | Yes
|  |  | 13 | Select Yes/No for SMS Alert | Yes
|  |  | 14 | Enter Pin/Zip code | 6411095
|  |  | 15 | Select State | TamilNadu
|  |  | 16 | Select District | Coimbatore
|  |  | 17 | Select Tehsil | Thondamuthur
|  |  | 18 | Enter City or Village | Devarayapuram 123
|  |  | 19 | Accept Terms & Conditions | Tick
|  |  | 20 | Click on Submit Buttom | Submit
|  |  | 21 | Enter OTP | Wrong OTP
TS_01_TC_03 | To check the Functionalities of Registration Module with Valid and Invalid data. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should not able to do register with Valid & Invalid data. | User is able to do registration with Valid and Invalid data. | Failed. |  |  | After Inputing valid and invalid data user can able to login and navigate to verfication Page. | Wrong Functional Defect.
|  | 2. Internet must be Available. | 2 | Click on Registration Button. | Click
|  | 3. Web Browser must be working. | 3 | Enter Full Name | Pradeep
|  | 4. URL must be working. | 4 | Enter Email | Pradeep33reigns@gmail.comm
|  | 5. Registration button must be clickable. | 5 | Enter Mobile Number | 123456789
|  |  | 6 | Create Password | Pradeep@001
|  |  | 7 | Select BloodGroup | O+
|  |  | 8 | Select Gender | Male
|  |  | 9 | Select DOB | 2000-02-29
|  |  | 10 | Select Weight | 610
|  |  | 11 | Select Last Donation Date | 2023-11-03
|  |  | 12 | Select Yes/No for Show Mobile | Yes
|  |  | 13 | Select Yes/No for SMS Alert | Yes
|  |  | 14 | Enter Pin/Zip code | 6411095
|  |  | 15 | Select State | TamilNadu
|  |  | 16 | Select District | Coimbatore
|  |  | 17 | Select Tehsil | Thondamuthur
|  |  | 18 | Enter City or Village | Devarayapuram
|  |  | 19 | Accept Terms & Conditions | Tick
|  |  | 20 | Click on Submit Buttom | Submit
|  |  | 21 | Enter OTP | OTP
TS_01_TC_04 | To check the Functionalities of Registration Module with Blank data. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should not able to do registered with blank data. | User should not able to do registered with blank data.User should receive error message that i.e. Please fill out the field. | Passed.
|  | 2. Internet must be Available. | 2 | Click on Registration Button. | Click
|  | 3. Web Browser must be working. | 3 | Enter Full Name
|  | 4. URL must be working. | 4 | Enter Email
|  | 5. Registration button must be clickable. | 5 | Enter Mobile Number
|  |  | 6 | Create Password
|  |  | 7 | Select BloodGroup
|  |  | 8 | Select Gender
|  |  | 9 | Select DOB
|  |  | 10 | Select Weight
|  |  | 11 | Select Last Donation Date
|  |  | 12 | Select Yes/No for Show Mobile
|  |  | 13 | Select Yes/No for SMS Alert
|  |  | 14 | Enter Pin/Zip code
|  |  | 15 | Select State
|  |  | 16 | Select District
|  |  | 17 | Select Tehsil
|  |  | 18 | Enter City or Village
|  |  | 19 | Accept Terms & Conditions
|  |  | 20 | Click on Submit Buttom | Submit
|  |  | 21 | Enter OTP
TS_01_TC_05 | To check the Functionalities of Registration Module with Mandatory data. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should able to register with mandatory data. | User should not able to do registered with mandatory data.User should receive error message for mandatory i.e. Please fill out the field. | Failed. |  |  | After inputing the mandatory data system asking for more details of the user. | Wrong Funtional Defect
|  | 2. Internet must be Available. | 2 | Click on Registration Button. | Click
|  | 3. Web Browser must be working. | 3 | Enter Full Name | Pradeep
|  | 4. URL must be working. | 4 | Select BloodGroup | O+
|  | 5. Registration button must be clickable. | 5 | Select Gender | Male
|  |  | 6 | Select Weight | 61
|  |  | 7 | Select Yes/No for SMS Alert | Yes
|  |  | 8 | Click on Submit Buttom | Click
|  |  | 9 | Enter OTP | OTP
TS_01_TC_06 | To check the Functionalities of Registration Module with Optionl data. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should not able to do register only with optional data | User should not able to do register only with optional data.User should receive error message for mandatory i.e. Please fill out the field. | Passed.
|  | 2. Internet must be Available. | 2 | Click on Registration Button. | Click
|  | 3. Web Browser must be working. | 3 | Enter Email | pradeep33reigns@gmail.com
|  | 4. URL must be working. | 4 | Enter Mobile Number | 7395835653
|  | 5. Registration button must be clickable. | 5 | Create Password | Pradeep@001
|  |  | 6 | Select DOB | 2000-02-29
|  |  | 7 | Select Last Donation Date | 2023-11-03
|  |  | 8 | Select Yes/No for Show Mobile | Yes
|  |  | 9 | Enter Pin/Zip code | 641109
|  |  | 10 | Select State | TamilNadu
|  |  | 11 | Select District | Coimbatore
|  |  | 12 | Select Tehsil | Thondamuthur
|  |  | 13 | Enter City or Village | Devarayapuram
|  |  | 14 | Accept Terms & Conditions | Tick
|  |  | 15 | Click on Submit Buttom | Submit
|  |  | 16 | Enter OTP | OTP
TS_01_TC_07 | To check the Functionalities of Registration Module with already Registered account. | 1. System must be working. | 1 | Enter URL | https://bloodbanktoday.com/ | User should not able to do register only with already registered account details. User should receive error message i.e. This Mobile No or Email Already Registered. | User should not able to do registration with already used Mobile Number and Email ID. | Passed.
|  | 2. Internet must be Available. | 2 | Click on Registration Button. | Click
|  | 3. Web Browser must be working. | 3 | Enter Full Name | Pradeep
|  | 4. URL must be working. | 4 | Enter Email | Pradeep33reigns@gmail.com
|  | 5. Registration button must be clickable. | 5 | Enter Mobile Number | 7395835653
|  |  | 6 | Create Password | Pradeep@001
|  |  | 7 | Select BloodGroup | O+
|  |  | 8 | Select Gender | Male
|  |  | 9 | Select DOB | 2000-02-29
|  |  | 10 | Select Weight | 70
|  |  | 11 | Select Last Donation Date | 2023-11-03
|  |  | 12 | Select Yes/No for Show Mobile | Yes
|  |  | 13 | Select Yes/No for SMS Alert | Yes
|  |  | 14 | Enter Pin/Zip code | 641109
|  |  | 15 | Select State | TamilNadu
|  |  | 16 | Select District | Coimbatore
|  |  | 17 | Select Tehsil | Thondamuthur
|  |  | 18 | Enter City or Village | Devarayapuram
|  |  | 19 | Accept Terms & Conditions | Tick
|  |  | 20 | Click on Submit Buttom | Submit
|  |  | 21 | Enter OTP | OTP
TS_02_TC_01 | To check the Functionalities of Login Module with Valid data. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should Login successfully & navigate to home page after entering the valid data. | User should able to login with valid data. | Passed.
|  | 2. Internet must be Available. | 2 | Click on Login Button. | Click
|  | 3. Web Browser must be working. | 3 | Enter Email and Mobile Number | pradeep33reigns@gmail.com
|  | 4. URL must be working. | 4 | Enter Password | Pradeep@001
|  | 5. User must be registered user | 5 | Click on Sign In Button | Click
6. Login button must be clickable.
TS_02_TC_02 | To check the Functionalities of Login Module with Invalid data. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should not able to navigate to Home Page. User should error message i.e. Wrong Username or Password. | User should able to login with invalid data. | Passed.
|  | 2. Internet must be Available. | 2 | Click on Login Button. | Click
|  | 3. Web Browser must be working. | 3 | Enter Email and Mobile Number | pradeep33reigns@gmail.com123
|  | 4. URL must be working. | 4 | Enter Password | loook
|  | 5. User must be registered user | 5 | Click on Sign In Button | Click
6. Login button must be clickable.
TS_02_TC_03 | To check the Functionalities of Login Module with Valid and Invalid data. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should not able to Login and navigate to home page if we are entering the wrong data. user should receieve error message i.e. wrong user name or password. | User is able to do login with Valid and Invalid data. | Passed.
|  | 2. Internet must be Available. | 2 | Click on Login Button. | Click
|  | 3. Web Browser must be working. | 3 | Enter Email and Mobile Number | pradeep33reigns@gmail.com
|  | 4. URL must be working. | 4 | Enter Password | 1455
|  | 5. User must be registered user | 5 | Click on Sign In Button | Click
6. Login button must be clickable.
TS_02_TC_04 | To check the Functionalities of Login Module with Blank data. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should not able to Login and navigate to home page if we are trying to login with empty data. user should receieve error message i.e. Please fill out field | User should not able to do login without entering data. | Passed.
|  | 2. Internet must be Available. | 2 | Click on Login Button. | Click
|  | 3. Web Browser must be working. | 3 | Enter Email and Mobile Number
|  | 4. URL must be working. | 4 | Enter Password
|  | 5. User must be registered user | 5 | Click on Sign In Button | Click
6. Login button must be clickable.
TS_02_TC_05 | To check the Functionalities of Login Module with Autofill. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should receive autofill for already use credential and with that credential user should move to home page. | User should able to login if user set the autofill option. | Passed.
|  | 2. Internet must be Available. | 2 | Click on Login Button. | Click
|  | 3. Web Browser must be working. | 3 | Enter Email and Mobile Number | pradeep33reigns@gmail.com
|  | 4. URL must be working. | 4 | Enter Password | Pradeep@001
|  | 5. User must be registered user | 5 | Click on Sign In Button | Click
6. Login button must be clickable.
TS_02_TC_06 | To check the Functionalities of Login Module with Forgot your password with Member ID | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | With the help of Member ID user should able to change the password. | User should not able to change the password with memberid. System asking for 10 digit of Member id which is not provided by system. | Failed. |  |  | After click on forgot your password button system asking to select any option for Recovery password. When user click on Member Id system asked enter Member ID but Member ID is not provided by system. | Wrong Functional Defect.
|  | 2. Internet must be Available. | 2 | Click on Login Button. | Click
|  | 3. Web Browser must be working. | 3 | Click on forgot your password | Click
|  | 4. URL must be working. | 4 | Enter Member ID | Member ID
|  | 5. User must be registered user | 5 | Click on Send message | Click
6. Login button must be clickable.
TS_02_TC_07 | To check the Functionalities of Login Module with Forgot your password with Login ID. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | With the help of Login ID user should able to change the password. | User should not able to change the password with Login ID. System asking for 10 digit of Login IDwhich is not provided by system. | Failed. |  |  | After clicking on forgot your password system asking to select any option for Recovery password. When user click on Login ID system asked enter Login ID but Login ID is not provided by system. | Wrong Functional Defect.
|  | 2. Internet must be Available. | 2 | Click on Login Button. | Click
|  | 3. Web Browser must be working. | 3 | Click on forgot your password | Click
|  | 4. URL must be working. | 4 | Click on Login ID | Click
|  | 5. User must be registered user | 5 | Enter Login ID | Login ID
|  | 6. Login button must be clickable. | 6 | Click on Send message | Click
TS_02_TC_08 | To check the Functionalities of Login Module with Forgot your password with Email ID. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | With the help of Email ID user should able to change the password. | User should not able to recover password with Email ID. | Failed. |  |  | After clicking on forgot your password system asked select any option for Recovery password. When user click on Email ID and input existing email Id then click on send Email button system display message with valid user Name, Mobile No. and Email id and then user click on send messge button after that system asked enter otp but user should not getting any otp on his registered Email id. | Wrong Functional Defect.
|  | 2. Internet must be Available. | 2 | Click on Login Button. | Click
|  | 3. Web Browser must be working. | 3 | Click on forgot your password | Click
|  | 4. URL must be working. | 4 | Click on Email ID | Click
|  | 5. User must be registered user | 5 | Enter Email ID | Pradeep33reigns@gmail.com
|  | 6. Login button must be clickable. | 6 | Click on Send message | Click
TS_02_TC_09 | To check the Functionalities of Login Module with Forgot your password with Mobile No. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | With the help of Mobile No user should able to change the password. | User should not able to recover password with Mobile No. | Failed. |  |  | After clicking on forgot your password system asked select any option for Recovery password. When user entered a mobile no. system display message send verify code for You are(User name), mobile number and Email ID. Then user click on send message button system ask to Enter OTP but user not getting any OTP on registered mobile number which user receive on Dashboard. | Wrong Functional Defect.
|  | 2. Internet must be Available. | 2 | Click on Login Button. | Click
|  | 3. Web Browser must be working. | 3 | Click on forgot your password | Click
|  | 4. URL must be working. | 4 | Click on Mobile No | Click
|  | 5. User must be registered user | 5 | Enter Mobile No | 7395835653
|  | 6. Login button must be clickable. | 6 | Click on Send message | Click
TS_02_TC_10 | To check the Functionalities of Login Module with Sign in with Facebook. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | Cursor should move to the facebook window, where user will enter sign in credentials. | User should not able to Login with Facebook. | Failed. |  |  | When user click on sign in with facebook button so that button is not working. | Wrong Functional Defect.
|  | 2. Internet must be Available. | 2 | Click on Login Button. | Click
|  | 3. Web Browser must be working. | 3 | Click on Facebook | Click
4. URL must be working.
5. User must be registered user
6. Login button must be clickable.
TS_02_TC_11 | To check the Functionalities of Login Module with Sign up now | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should navigate to Registration Portal when clicked on Sign up now. | User should able to do Login with Sign Up Now but OTP is not working. | Partial Failed. |  |  | After clicking on signup button system is navigate to registration portal and user fill out all the details and click on submit button sytem asking for OTP which user received on Dashboard rather than registered mobile no. | Wrong Functional Defect.
|  | 2. Internet must be Available. | 2 | Click on Login Button. | Click
|  | 3. Web Browser must be working. | 3 | Click on Sign up now | Click
4. URL must be working.
5. User must be registered user
6. Login button must be clickable.
TS_02_TC_12 | To check the Functionalities of Login Module with with Back to Website. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should navigate to website home page blood bank today when clicked on Back To Website. | User should able to navigate on home page i.e. Blood Bank today | Passed.
|  | 2. Internet must be Available. | 2 | Click on Login Button. | Click
|  | 3. Web Browser must be working. | 3 | Click on Back to Website | Click
4. URL must be working.
5. User must be registered user
6. Login button must be clickable.
TS_02_TC_13 | To check the Functionalities of Login Module with without Registration. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should not able to login without registration. | User should not able to login without registration. | Passed.
|  | 2. Internet must be Available. | 2 | Click on Login Button. | Click
|  | 3. Web Browser must be working. | 3 | Click on without Registration. | Click
4. URL must be working.
5. User must be registered user
6. Login button must be clickable.
TS_03_TC_01 | To check the Functionalities of Find Blood Module with Blood Group. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | With only blood group, user should not find blood. user should receive error message i.e please select district. | User should not able to find blood with only blood group. | Failed. |  |  | When user is click on find blood button system asking for enter the blood group but after entering the blood group system asking for enter state, district and tehsil. | Wrong Functional Defect.
|  | 2. Internet must be Available. | 2 | Select Blood Group | O+
|  | 3. Web Browser must be working. | 3 | Select State
|  | 4. URL must be working. | 4 | Select District
|  | 5. Find Blood button must be Clickable. | 5 | Select Tehsil
|  |  | 6 | Click on Find Blood | Click
TS_03_TC_02 | To check the Functionalities of Find Blood Module with Blood Group and State. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | With only blood group and state, user should not find blood. user should receive error message i.e please select district. | User should not able to find blood with only blood group and state. | Failed. |  |  | When user is click on blood group button and state button and inputing the details system asking for district and tehsil. | Wrong Functional Defect.
|  | 2. Internet must be Available. | 2 | Select Blood Group | O+
|  | 3. Web Browser must be working. | 3 | Select State | TamilNadu
|  | 4. URL must be working. | 4 | Select District
|  | 5. Find Blood button must be Clickable. | 5 | Select Tehsil
|  |  | 6 | Click on Find Blood | Click
TS_03_TC_03 | To check the Functionalities of Find Blood Module with Blood Group, State and District. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | With blood group , state and district, user should able to find blood as per selected location. | When user is click on blood group button,state button and district button and inputing the details system asking for tehsil. | Passed.
|  | 2. Internet must be Available. | 2 | Select Blood Group | O+
|  | 3. Web Browser must be working. | 3 | Select State | TamilNadu
|  | 4. URL must be working. | 4 | Select District | Coimbatore
|  | 5. Find Blood button must be Clickable. | 5 | Select Tehsil
|  |  | 6 | Click on Find Blood | Click
TS_03_TC_04 | To check the Functionalities of Find Blood Module with Blood Group, State, District and Tehsil. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | With blood group , state , district and teshsil user should able to find blood as per selected location. | When user is click on blood group button,state button ,district button and tehsil button and inputing the details and submitting the details,u ser should able to find blood as per selected location. | Passed.
|  | 2. Internet must be Available. | 2 | Select Blood Group | O+
|  | 3. Web Browser must be working. | 3 | Select State | TamilNadu
|  | 4. URL must be working. | 4 | Select District | Coimbatore
|  | 5. Find Blood button must be Clickable. | 5 | Select Tehsil | Thondamuthur
|  |  | 6 | Click on Find Blood | Click
TS_03_TC_05 | To check the Functionalities of Find Blood Module with empty fields. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should not find blood with blank entries. user should receieve the error message i.e. please select blood group. | User should not find blood with blank entries. | Passed.
|  | 2. Internet must be Available. | 2 | Select Blood Group
|  | 3. Web Browser must be working. | 3 | Select State
|  | 4. URL must be working. | 4 | Select District
|  | 5. Find Blood button must be Clickable. | 5 | Select Tehsil
|  |  | 6 | Click on Find Blood | Click
TS_04_TC_01 | To check the Functionalities of Request Blood Module with Valid data. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should able to request blood with vaild data. | User is able to request blood with Valid data but OTP is not working. Which is asking by the system for account verfication after clicking on Submit button. | Partially Failed. |  |  | After clicking on submit button system asking for OTP which user recevied on Dashboard rather than registered mobile number. | Wrong Functional Defect.
|  | 2. Internet must be Available. | 2 | Click on Request Blood | Click
|  | 3. Web Browser must be working. | 3 | Enter Patient Name | Pradeep
|  | 4. URL must be working. | 4 | Enter Doctor Name | Dr. Ajay Gaikwad
|  | 5. Request Blood button must be Clickable. | 5 | Select Blood Group | O+
|  |  | 6 | Select State | TamilNadu
|  |  | 7 | Select District | Coimbatore
|  |  | 8 | Select Tehsil | Thondamuthur
|  |  | 9 | Enter Hospital Name and Address | Gold Care Hospital Sr no 101 /102 PN Classic , Devarayapuram Rd, Tilak Colony, TamilNadu 9th Block,TamilNadu ,Coimbatore,Thondamuthur 641109
|  |  | 10 | Enter Contact Name | Pradeep C
|  |  | 11 | Enter Mobile Number | 7395835653
|  |  | 12 | Enter Date when need | 6/30/2023
|  |  | 13 | Select Priorty | Early
|  |  | 14 | Enter Email | Pradeep123@gmail.com
|  |  | 15 | Enter other message | please help as soon as possible with blood
|  |  | 16 | Click Send Request | Click
TS_04_TC_02 | To check the Functionalities of Request Blood Module with Invalid data. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should not able to request blood with invaild data. | User is able to request blood with Invalid data | Failed. |  |  | Fields like Patient Name,Doctor name should accept alphabets but in actual it is taking alphanumeric , Email is taking with wrong domain, Mobile no taking more than 10 digit. | Wrong Functional Defect.
|  | 2. Internet must be Available. | 2 | Click on Request Blood | Click
|  | 3. Web Browser must be working. | 3 | Enter Patient Name | Pradeep76r
|  | 4. URL must be working. | 4 | Enter Doctor Name | Dr. Ajay Gaikwad855
|  | 5. Request Blood button must be Clickable. | 5 | Select Blood Group | O+
|  |  | 6 | Select State | TamilNadu
|  |  | 7 | Select District | Coimbatore
|  |  | 8 | Select Tehsil | Thondamuthur
|  |  | 9 | Enter Hospital Name and Address | Gold Care Hospital Sr no 101 /102 PN Classic , Devarayapuram Rd, Tilak Colony, TamilNadu 9th Block,TamilNadu ,Coimbatore,Thondamuthur 641109
|  |  | 10 | Enter Contact Name | Pradeep C 423
|  |  | 11 | Enter Mobile Number | 70583112@g
|  |  | 12 | Enter Date when need | 6/30/2023
|  |  | 13 | Select Priorty | Early
|  |  | 14 | Enter Email | anutiwari09@gafmail.com
|  |  | 15 | Enter other message | please help as soon as possible with blood
|  |  | 16 | Click Send Request | Click
TS_04_TC_03 | To check the Functionalities of Request Blood Module with Valid and Invalid data. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should not able to Request Blood with Valid and Invalid data. | User is able to do request blood with Valid and Invalid data. | Failed. |  |  | After Inputing valid and invalid data user can able to login and navigate to verfication Page. | Wrong Functional Defect.
|  | 2. Internet must be Available. | 2 | Click on Request Blood | Click
|  | 3. Web Browser must be working. | 3 | Enter Patient Name | Pradeep
|  | 4. URL must be working. | 4 | Enter Doctor Name | Dr. Ajay Gaikwad.
|  | 5. Request Blood button must be Clickable. | 5 | Select Blood Group | O+
|  |  | 6 | Select State | TamilNadu
|  |  | 7 | Select District | Coimbatore
|  |  | 8 | Select Tehsil | Thondamuthur
|  |  | 9 | Enter Hospital Name and Address | Gold Care Hosp22ital Sr no 101 /102 PN Classic , Devarayapuram Rd, Tilak Colony, TamilNadu 9th Block,TamilNadu ,Coimbatore,Thondamuthur 641109
|  |  | 10 | Enter Contact Name | Pradeep C252
|  |  | 11 | Enter Mobile Number | 7824189810#
|  |  | 12 | Enter Date when need | 6/30/2023
|  |  | 13 | Select Priorty | Early
|  |  | 14 | Enter Email | Manutiwari09@gafmail.com
|  |  | 15 | Enter other message | please help as soon as possible with blood
|  |  | 16 | Click Send Request | Click
TS_04_TC_04 | To check the Functionalities of Request Blood Module with blank data. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should not able to Request Blood with Blank data. | User should not able to do request blood with blank data..User should receive error message that i.e. Please fill out the field. | Passed.
|  | 2. Internet must be Available. | 2 | Click on Request Blood | Click
|  | 3. Web Browser must be working. | 3 | Enter Patient Name
|  | 4. URL must be working. | 4 | Enter Doctor Name
|  | 5. Request Blood button must be Clickable. | 5 | Select Blood Group
|  |  | 6 | Select State
|  |  | 7 | Select District
|  |  | 8 | Select Tehsil
|  |  | 9 | Enter Hospital Name and Address
|  |  | 10 | Enter Contact Name
|  |  | 11 | Enter Mobile Number
|  |  | 12 | Enter Date when need
|  |  | 13 | Select Priorty
|  |  | 14 | Enter Email
|  |  | 15 | Enter other message | please help as soon as possible with blood
|  |  | 16 | Click Send Request | Click
TS_04_TC_05 | To check the Functionalities of Request Blood Module with Mandatory data. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should able to request blood with mandatory data. | User can able to request with mandatory data. | Failed. |  |  | After click on send request button system display message enter message code for mobile number verification but user not gettting any code. | Wrong Functional Defect.
|  | 2. Internet must be Available. | 2 | Click on Request Blood | Click
|  | 3. Web Browser must be working. | 3 | Enter Patient Name | Pradeep
|  | 4. URL must be working. | 4 | Enter Doctor Name | Dr. Ajay Gaikwad.
|  | 5. Request Blood button must be Clickable. | 5 | Select Blood Group | O+
|  |  | 6 | Enter Hospital Name and Address | Gold Care Hospital Sr no 101 /102 PN Classic , Devarayapuram Rd, Tilak Colony, TamilNadu 9th Block,TamilNadu ,Coimbatore,Thondamuthur 641109
|  |  | 7 | Enter Contact Name | Pradeep C
|  |  | 8 | Enter Mobile Number | 7395835653
|  |  | 9 | Enter Date when need | 6/30/2023
|  |  | 10 | Select Priorty | Early
|  |  | 11 | Enter Email | Pradeep123@gmail.com
|  |  | 12 | Enter other message | please help as soon as possible with blood
TS_04_TC_06 | To check the Functionalities of Request Blood Module with Optional data. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should not ble to request blood with optional data. | User should not able to request blood with optional data.User should receive error message for optional data i.e. Please fill out the field. | Passed.
|  | 2. Internet must be Available. | 2 | Click on Request Blood | Click
|  | 3. Web Browser must be working. | 3 | Select State | TamilNadu
|  | 4. URL must be working. | 4 | Select District | Coimbatore
|  | 5. Request Blood button must be Clickable. | 5 | Select Tehsil | Thondamuthur
|  |  | 6 | Enter other message | please help as soon as possible with blood
|  |  | 7 | Click Send Request | Click
TS_04_TC_07 | To check the Functionalities of Request Blood Module with Recent Donor Join data. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | System should display the recent donor list. | User can able to see the details of recent donar join data. | Passed.
|  | 2. Internet must be Available. | 2 | Click on Request Blood | Click
|  | 3. Web Browser must be working. | 3 | Check Recent Donor in recent donor list | Checking loookli in recent donor
4. URL must be working.
5. Request Blood button must be Clickable.
TS_05_TC_01 | To test the fuctionalities of Blood Bank module with Select State. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should find the Blood bank with state only. | User should get a details of Blood in TamilNadu. | Passed.
|  | 3. Web Browser must be working. | 2 | Select State. | TamilNadu
|  | 4. URL must be working. | 3 | Click on Search Button. | Click
5. Blood Bank button must be Clickable.
TS_05_TC_02 | To check the Functionalities of Blood Bank Module with State and District. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should find the Blood bank with state and district also. | User should find the Blood with State and District. | Passed.
|  | 3. Web Browser must be working. | 2 | Select State. | TamilNadu
|  | 4. URL must be working. | 3 | Select District | Coimbatore
|  | 5. Blood Bank button must be Clickable. | 4 | Click on Search Button. | Click
TS_05_TC_03 | To check the Functionalities of Blood Bank Module with empty fields. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should not able to find Blood bank with blank fields, System generate message plz select state. | User should not able to search blood if we are trying to login with empty data. user should receive error message i.e. Please select the state. | Passed
|  | 3. Web Browser must be working. | 2 | Select State.
|  | 4. URL must be working. | 3 | Select District
|  | 5. Blood Bank button must be Clickable. | 4 | Click on Search Button. | Click
TS_06_TC_01 | To check the Functionalities of Blogs Module with Hyperlink i.e. By Blood Bank today. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should able to click on that link i.e. By Blood Bank today. | User should not able to get the details of By Blood Bank today link system shows error message. | Failed. |  |  | When user click on By Blood Bank today, it shows server error i.e. 404- File or Directory not found. | Wrong Fuctional Defect.
|  | 3. Web Browser must be working. | 2 | Click on Blogs | Click
|  | 4. URL must be working. | 3 | Click on Hyperlink By Blood Bank today | Click
5. Blogs button must be Clickable.
TS_06_TC_02 | To check the Functionalities of Blogs Module with Facebook Share. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should able to navigate on facebook share page. User can also login with there Facebook account. | After Clicking on Facebook Share button user should able to navigate on facebook share page. User can also login with there Facebook account. | Passed.
|  | 3. Web Browser must be working. | 2 | Click on Blogs | Click
|  | 4. URL must be working. | 3 | Click on Facebook Share Button | Click
5. Blogs button must be Clickable.
TS_06_TC_03 | To check the Functionalities of Blogs Module with Whatsapp Share. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should not able to click WhatsApp share Button. | After Clicking on Whatsapp button user should not able to navigate on WhatsApp share page button, and whatsApp share button is not working. | Failed. |  |  | When user click on WhatsApp share button, then that button is not working user still in Blogs page only. | Wrong Functional Defect.
|  | 3. Web Browser must be working. | 2 | Click on Blogs | Click
|  | 4. URL must be working. | 3 | Click on Whatsapp Share Button | Click
5. Blogs button must be Clickable.
TS_06_TC_04 | To check the Functionalities of Blogs Module with Read More. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should able to click Read More Button. | After Clicking on Read More button user should able to click on Read more button, and user can able to read the further details. | Passed.
|  | 3. Web Browser must be working. | 2 | Click on Blogs | Click
|  | 4. URL must be working. | 3 | Click on Read More Button. | Click
5. Blogs button must be Clickable.
TS_06_TC_05 | To check the Functionalities of Blogs Module with Reetack. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should able to navigate on home page i.e. Blood Bank Today. | After clicking on REETACk button user should able to navigate on home page i.e. Blood Bank Today. | Passed.
|  | 3. Web Browser must be working. | 2 | Click on Blogs | Click
|  | 4. URL must be working. | 3 | Click on REETACK Button. | Click
5. Blogs button must be Clickable.
TS_06_TC_06 | To check the Functionalities of Blogs Module with Web Solution Company Hyperlink. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should not able to click on Web Solution Company Button. | After clicking on Web Solution Company Hyperlink user should not able to Access the Hyperlink, because Hyperlink is not working. | Failed. |  |  | When user click on Web Solution Company Hyperlink button, then that button is not working user still in Blog page only. | Wrong Functional Defect.
|  | 3. Web Browser must be working. | 2 | Click on Blogs | Click
|  | 4. URL must be working. | 3 | Click on Web Solution Company Button. | Click
5. Blogs button must be Clickable.
TS_06_TC_07 | To check the Functionalities of Blogs Module with Visit Icon. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should able to click on Visit Button. | After clicking on Visit button user should not able to search given history on Web solution company. | Partial Failed. |  |  | When user click on the visit icon user not getting any details of the mentioned link i.e. Web Solutions Company instead of that user should nevigate on the home page i.e. Blood Bank Today. | Wrong Functional Defect.
|  | 3. Web Browser must be working. | 2 | Click on Blogs | Click
|  | 4. URL must be working. | 3 | Click on Visit Button. | Click
5. Blogs button must be Clickable.
TS_06_TC_08 | To check the Functionalities of Blogs Module with Share Icon. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should not able to click on Share Icon. | After clicking on share icon of Web solution company user should not able to click on share icon because icon is not working. | Failed. |  |  | When user click on share icon of Web solution company button, then that button is not working user still in Blog page only. | Wrong Functional Defect.
|  | 3. Web Browser must be working. | 2 | Click on Blogs | Click
|  | 4. URL must be working. | 3 | Click on Share Icon. | Click
5. Blogs button must be Clickable.
TS_07_TC_01 | To check the Functionalities of Causes Module with Facebook Share. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should able to navigate on facebook share page. User can also login with there Facebook account. | After Clicking on Facebook Share button user should able to navigate on facebook share page. User can also login with there Facebook account. | Passed.
|  | 3. Web Browser must be working. | 2 | Click on Causes | Click
|  | 4. URL must be working. | 3 | Click on Facebook Share. | Click
5. Causes button must be Clickable.
TS_07_TC_02 | To check the Functionalities of Causes Module with Whatsapp Share. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should not able to click WhatsApp share Button. | After Clicking on Whatsapp button user should not able to navigate on WhatsApp share page button, and whatsApp share button is not working. | Failed. |  |  | When user click on WhatsApp share button, then that button is not working user still in causes page only. | Wrong Functional Defect.
|  | 3. Web Browser must be working. | 2 | Click on Causes | Click
|  | 4. URL must be working. | 3 | Click on Whatsapp Share | Click
5. Causes button must be Clickable.
TS_07_TC_03 | To check the Functionalities of Causes Module with Donate Now. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should able to navigate to the Donate now page. | After clicking on donate now button user should able to make a donation with paytm and barcode is visible to make payment. | Passed.
|  | 3. Web Browser must be working. | 2 | Click on Causes | Click
|  | 4. URL must be working. | 3 | Click on Donate now | Click
5. Causes button must be Clickable.
TS_07_TC_04 | To check the Functionalities of Causes Module with More Detail. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should able to click More Detail Button. | After Clicking on More detail button user should able to click on more detail button, and user can able to read the further details .i.e. about cause or Eradicate Blood Shortage. | Passed.
|  | 3. Web Browser must be working. | 2 | Click on Causes | Click
|  | 4. URL must be working. | 3 | Click on More Detail | Click
5. Causes button must be Clickable.
TS_07_TC_05 | To check the Functionalities of Causes Module with Visit Also. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should not able to click on Visit Also. | After Clicking no visit also user should not able to click on visit also. | Failed. |  |  | When user click on Visit also button, then that button is not working user still in causes page only. | Wrong Functional Defect.
|  | 3. Web Browser must be working. | 2 | Click on Causes | Click
|  | 4. URL must be working. | 3 | Click on Visit Also | Click
5. Causes button must be Clickable.
TS_08_TC_01 | To check the Functionalities of Events Module with Facebook Share. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should able to click on Event button. User can also navigate the Facebook share. | After Clicking on Events button user should able to navigate on facebook share page. User can also login with there Facebook account. | Passed.
|  | 3. Web Browser must be working. | 2 | Click on Events | Click
|  | 4. URL must be working. | 3 | Click on Facebook Share | Click
5. Events button must be Clickable.
TS_08_TC_02 | To check the Functionalities of Events Module with Whatsapp Share. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should not able to click WhatsApp share Button. | After Clicking on Whatsapp button user should not able to navigate on WhatsApp share page button, and whatsApp share button is not working. | Failed. |  |  | When user click on WhatsApp share button, then that button is not working user still in event page only. | Wrong Functional Defect.
|  | 3. Web Browser must be working. | 2 | Click on Events | Click
|  | 4. URL must be working. | 3 | Click on Whatsapp Share. | Click
5. Events button must be Clickable.
TS_08_TC_03 | To check the Functionalities of Events Module with Read More. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should able to click Read More Button. | After Clicking on Read More button user should able to click on Read more button, and user can able to read the further details. | Passed.
|  | 3. Web Browser must be working. | 2 | Click on Events | Click
|  | 4. URL must be working. | 3 | Click on Read More. | Click
5. Events button must be Clickable.
TS_08_TC_04 | To check the Functionalities of Events Module with Visit Also. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should not able to click on Visit Also. | After Clicking no visit also user should not able to click on visit also. | Failed. |  |  | When user click on Visit also button, then that button is not working user still in event page only. | Wrong Functional Defect.
|  | 3. Web Browser must be working. | 2 | Click on Events | Click
|  | 4. URL must be working. | 3 | Click on Visit also. | Click
5. Events button must be Clickable.
TS_08_TC_05 | To check the Functionalities of Events Module with Hyperlink i.e By Jayant Bansal. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should able to see the profile of By Jayant Bansal. | fter clickling on Hyperlink i.e By Jayant Bansal user should able to see the details. | Passed.
|  | 3. Web Browser must be working. | 2 | Click on Events | Click
|  | 4. URL must be working. | 3 | Click on By Jayant Bansal. | Click
5. Events button must be Clickable.
TS_09_TC_01 | To check the Functionalities of News Module with Facebook Share. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should able to navigate on facebook share page. User can also login with there Facebook account. | After Clicking on Facebook Share button user should able to navigate on facebook share page. User can also login with there Facebook account. | Passed.
|  | 3. Web Browser must be working. | 2 | Click on News | Click
|  | 4. URL must be working. | 3 | Click on Facebook Share | Click
5. News button must be Clickable.
TS_09_TC_02 | To check the Functionalities of News Module with Hyperlink i.e By Lakhvinder Singh | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should able to see the details of Lakhvinder Singh's profile. | After clickling on Hyperlink i.e By Lakhvinder Singh user should able to see the details. | Passed.
|  | 3. Web Browser must be working. | 2 | Click on News | Click
|  | 4. URL must be working. | 3 | By Lakhvinder Singh | Click
5. News button must be Clickable.
TS_09_TC_03 | To check the Functionalities of News Module with Whatsapp Share. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should not able to click WhatsApp share Button. | After Clicking on Whatsapp button user should not able to navigate on WhatsApp share page button, and whatsApp share button is not working. | Failed. |  |  | When user click on WhatsApp share button, then that button is not working user still in News page only. | Wrong Functional Defect.
|  | 3. Web Browser must be working. | 2 | Click on News | Click
|  | 4. URL must be working. | 3 | Click on Whatsapp Share | Click
5. News button must be Clickable.
TS_09_TC_04 | To check the Functionalities of News Module with Read More. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should able to click Read More Button. | After Clicking on Read More button user should able to click on Read more button, and user can able to read the further details. | Passed.
|  | 3. Web Browser must be working. | 2 | Click on News | Click
|  | 4. URL must be working. | 3 | Click on Read More | Click
5. News button must be Clickable.
TS_09_TC_05 | To check the Functionalities of News Module with Visit Also. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should not able to click on Visit Also. | After Clicking no visit also user should not able to click on visit also. | Failed. |  |  | When user click on Visit also button, then that button is not working user still in News page only. | Wrong Functional Defect.
|  | 3. Web Browser must be working. | 2 | Click on News | Click
|  | 4. URL must be working. | 3 | Click on Visit Also | Click
5. News button must be Clickable.
TS_10_TC_01 | To check the Functionalities of Donate Us Module with QR Code. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should able to scan the QR Code. | User should able to scan the QR Code and able to Enter the amount. | Passed.
|  | 3. Web Browser must be working. | 2 | Click on Donate Us | Click
|  | 4. URL must be working. | 3 | Scan on QR Code | Scan
5. Donate us button must be Clickable.
TS_10_TC_02 | To check the Functionalities of Donate Us Module with Mobile number | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should able to Enter the Valid mobile number. | User should able to Enter the Valid mobile numbe and able to Enter the amount. | Passed.
|  | 3. Web Browser must be working. | 2 | Click on Donate Us | Click
|  | 4. URL must be working. | 3 | Enter UPI number | Enter
5. Donate us button must be Clickable.
TS_10_TC_03 | To check the Functionalities of Donate Us Module with Displayed amount | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should able to click on amount given by system and make payment. | User should able to click on that display amount and fill out fields then click on Donate now. Then system ask to choose payment options according to that user can donate money. | Passed.
|  | 3. Web Browser must be working. | 2 | Click on Donate Us | Click
|  | 4. URL must be working. | 3 | Click on Displayed Amount | Click
5. Donate us button must be Clickable.
TS_10_TC_04 | To check the Functionalities of Donate Us Module with Entering the amount Manually. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should not able to Donate Amount Manually. | After Clicking no donate us button user should not able to Donate Amount Manually. | Failed. |  |  | After filling the details and user enter the amount of 700 and click on donate now button but system not allowing of pay manual amount its navigate too system page. | Wrong Functional Defect.
|  | 3. Web Browser must be working. | 2 | Click on Donate Us | Click
|  | 4. URL must be working. | 3 | Enter Amount Manually. | 700
5. Donate us button must be Clickable.
TS_10_TC_05 | To check the Functionalities of Donate Us Module with Valid data. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should able to donate money with Valid data. | After inputing all the details user should able to donate money. | Passed.
|  | 3. Web Browser must be working. | 2 | Click on Donate Us. | Click
|  | 4. URL must be working. | 3 | Enter Full Name. | Pradeep
|  | 5. Donate us button must be Clickable. | 4 | Enter Email. | Pradeep33reigns@gmail.com
|  |  | 5 | Enter Mobile No. | 7395835653
|  |  | 6 | Enter Country. | India
|  |  | 7 | Enter State. | TamilNadu
|  |  | 8 | Enter City. | Coimbatore
|  |  | 9 | Enter Pin/Zip Code. | 641109
|  |  | 10 | Enter Address. | Gold Care Hospital Sr no 101 /102 PN Classic , Devarayapuram Rd, Tilak Colony, TamilNadu 9th Block,TamilNadu ,Coimbatore,Thondamuthur 641109
|  |  | 11 | Select Name in list. | Display
TS_10_TC_06 | To check the Functionalities of Donate Us Module with Invalid data. | 1. System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should not able to donate money with Invalid data. | User should not able to donate money with Invalid data, after click on Donate Us button system remain on same page. | Passed.
|  |  | 2 | Click on Donate Us. | Click
|  | 3. Web Browser must be working. | 3 | Select Amount | 100
|  | 4. URL must be working. | 4 | Enter Full Name. | Pradeep123
|  | 5. Donate us button must be Clickable. | 5 | Enter Email. | Padeep345@gmail.com
|  |  | 6 | Enter Mobile No. | 7395835653452
|  |  | 7 | Enter Country. | India
|  |  | 8 | Enter State. | TamilNadu
|  |  | 9 | Enter City. | Coimbatore
|  |  | 10 | Enter Pin/Zip Code. | 641109
|  |  | 11 | Enter Address. | Gold Care Hospital Sr no 101 /102 PN Classic , Devarayapuram Rd, Tilak Colony, TamilNadu 9th Block,TamilNadu ,Coimbatore,Thondamuthur 641109
|  |  | 12 | Select Name in list. | Display
TS_10_TC_07 | To check the fuctionalities of Donate Us module with Valid and Invalid Data. | 1.System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should not able to donate money with Valid and Invalid data. | User should not able to donate money with valid and Invalid data, user navigate on Choose a payment option page. | Failed. |  |  | When user enter invalid data for Full Name, Email, Country, State, City, Adress and Valid data for Mobile No, Pin/Zip code, user should able to donate money but system navigate on Choose a payment option page. | Wrong Fuctional Defect.
|  | 2. Internet must be available. | 2 | Click on Donate Us. | Click
|  | 3. Web Browser must be working. | 3 | Select Amount | 100
|  | 4. URL must be working. | 4 | Enter Full Name. | Pradeep
|  | 5. Donate Us button must be clickable. | 5 | Enter Email. | Padeep345@gmail.com
|  |  | 6 | Enter Mobile No. | 7395835653452
|  |  | 7 | Enter Country. | India
|  |  | 8 | Enter State. | TamilNadu
|  |  | 9 | Enter City. | Coimbatore
|  |  | 10 | Enter Pin/Zip Code. | 641109
|  |  | 11 | Enter Address. | Gold Care Hospital Sr no 101 /102 PN Classic , Devarayapuram Rd, Tilak Colony, TamilNadu 9th Block,TamilNadu ,Coimbatore,Thondamuthur 641109
|  |  | 12 | Select Name in list. | Display
TS_10_TC_08 | To check the fuctionalities of Donate Us module with Blank data. | 1.System must be working. | 1 | Enter URL. | https://www.bloodbanktoday.com | User should not donate money with Blank data. | User should not donate money with Blank data. System display message i.e. please fill out the fields. | Passed.
|  | 2. Internet must be available. | 2 | Click on Donate Us. | Click
|  | 3. Web Browser must be working. | 3 | Select Amount.
|  | 4. URL must be working. | 4 | Enter Full Name.
|  | 5. Donate Us button must be clickable. | 5 | Enter Email.
|  |  | 6 | Enter Mobile No.
|  |  | 7 | Enter Country.
|  |  | 8 | Enter State.
|  |  | 9 | Enter City.
|  |  | 10 | Enter Pin/Zip Code.
|  |  | 11 | Enter Address.
|  |  | 12 | Select Name in list. | Display
TS_10_TC_09 | To check the fuctionalities of Donate Us module with Mandatory Data. | 1.System must be working. | 1 | Enter URL. | https://www.bloodbanktoday.com | User should not able to donate money with mandatory data. | User should not able to donate money with mandatory data. System display message i.e. please fill out the fields. | Passed.
|  | 2. Internet must be available. | 2 | Click on Donate Us. | Click
|  | 3. Web Browser must be working. | 3 | Enter Full Name. | Pradeep
|  | 4. URL must be working. | 4 | Mobile No. | 7395835653
5. Donate Us button must be clickable.
TS_10_TC_10 | To check the fuctionalities of Donate Us module with Optional Data. | 1.System must be working. | 1 | Enter URL. | https://bloodbanktoday.com/ | User should not able to donate money with Optional Data. | User should not able to donate money with optional data. System display message i.e. please fill out the fields. | Passed.
|  | 2. Internet must be available. | 2 | Click on Donate Us. | Click
|  | 3. Web Browser must be working. | 3 | Select Amount. | 100
|  | 4. URL must be working. | 5 | Enter Email. | Pradeep33reigns@gmail.com
|  | 5. Donate Us button must be clickable. | 6 | Enter Country. | India
|  |  | 7 | Enter State. | India
|  |  | 8 | Enter City. | TamilNadu
|  |  | 9 | Enter Pin/Zip Code. | Coimbatore
|  |  | 10 | Enter Address. | 641109
|  |  | 11 | Select Name in list. | Display
TS_10_TC_11 | To check the fuctionalities of Donate Us module with Recent Donar Join Button. | 1.System must be working. | 1 | Enter URL. | https://www.bloodbanktoday.com | User should able to get the list of recently joined donars. | User should get the list of recently joined donars and join with them. | Passed.
|  | 2. Internet must be available. | 2 | Click on Donate Us. | Click
|  | 3. Web Browser must be working. | 3 | Click on Recent donor join. | Click
4. URL must be working.
5. Donate Us button must be clickable.
TS_10_TC_12 | To check the fuctionalities of Donate Us module with Scrolling Arrow. | 1.System must be working. | 1 | Enter URL. | https://www.bloodbanktoday.com | User should able to scroll up the page by cliking the scrolling arrow. | When user click on that scrolling arrow the page should goes up. User should able to scroll up the page by cliking the scrolling arrow. | Passed.
|  | 2. Internet must be available. | 2 | Click on Donate Us. | Click
|  | 3. Web Browser must be working. | 3 | Click on Scrolling Arrow. | Click
4. URL must be working.
5. Donate Us button must be clickable.
TS_11_TC_01 | To check the fuctionalities of My Message module with Three line button. | 1.System must be working. | 1 | Enter URL. | https://www.bloodbanktoday.com | User should able to check the My Message screen. | When user click on three line button, user should able to check the details and send message also. | Passed.
|  | 2. Internet must be available. | 2 | Click on Login Button. | Click
|  | 3. Web Browser must be working. | 3 | Enter Email ID or Mobile No. | Pradeep33reigns@gmail.com
|  | 4. URL must be working. | 4 | Enter Password. | loookli@123
|  | 5. My Messages button must be clickable. | 5 | Click on Sign In Button. | Click
|  |  | 6 | Click on My Message. | Click
|  |  | 7 | Click on three line Button. | Click
TS_11_TC_02 | To check the fuctionalities of My Messages module with My Reetack. | 1.System must be working. | 1 | Enter URL. | https://www.bloodbanktoday.com | User should navigate on Dashboard window. | After clicking on reetack user navigate on dashboard window. | Passed.
|  | 2. Internet must be available. | 2 | Click on Login Button. | Click
|  | 3. Web Browser must be working. | 3 | Enter Email ID or Mobile No. | Pradeep33reigns@gmail.com
|  | 4. URL must be working. | 4 | Enter Password. | loookli@123
|  | 5. My Messages button must be clickable. | 5 | Click on Sign In Button. | Click
|  |  | 6 | Click on My Message. | Click
|  |  | 7 | Click on Reetack button. | Click
TS_11_TC_03 | To check the fuctionalities of My Messages module with Back to website. | 1.System must be working. | 1 | Enter URL. | https://www.bloodbanktoday.com | User should navigate on Home page window .i.e. Blood Bank Today. | After clicking on back to website user should navigate on Home page window .i.e. Blood Bank Today. | Passed.
|  | 2. Internet must be available. | 2 | Click on Login Button. | Click
|  | 3. Web Browser must be working. | 3 | Enter Email ID or Mobile No. | Pradeep33reigns@gmail.com
|  | 4. URL must be working. | 4 | Enter Password. | loookli@123
|  | 5. My Messages button must be clickable. | 5 | Click on Sign In Button. | Click
|  |  | 6 | Click on My Message. | Click
|  |  | 7 | Click on Back to website. | Click
TS_11_TC_04 | To check the fuctionalities of My Messages module with Settings icon. | 1.System must be working. | 1 | Enter URL. | https://www.bloodbanktoday.com | User should able to click on setting icon and see the details of setting. | After clicking on settings icon from My Messages user should able to Fixed navbar, fixed main menu, Right-to-left direction, Main menu on the right, Hide main menu and changing the themes also. | Passed.
|  | 2. Internet must be available. | 2 | Click on Login Button. | Click
|  | 3. Web Browser must be working. | 3 | Enter Email ID or Mobile No. | Pradeep33reigns@gmail.com
|  | 4. URL must be working. | 4 | Enter Password. | loookli@123
|  | 5. My Messages button must be clickable. | 5 | Click on Sign In Button. | Click
|  |  | 6 | Click on My Message. | Click
|  |  | 7 | Click on Setting Icon. | Click
TS_11_TC_05 | To check the fuctionalities of My Messages module with Send message. | 1.System must be working. | 1 | Enter URL. | https://www.bloodbanktoday.com | User should able to send the message. | After clicking on send message user should able to send message by selecting message for, priority type and user should choose file also then click on send button. | Passed.
|  | 2. Internet must be available. | 2 | Click on Login Button. | Click
|  | 3. Web Browser must be working. | 3 | Enter Email ID or Mobile No. | Pradeep33reigns@gmail.com
|  | 4. URL must be working. | 4 | Enter Password. | loookli@123
|  | 5. My Messages button must be clickable. | 5 | Click on Sign In Button. | Click
|  |  | 6 | Click on My Message. | Click
|  |  | 7 | Click on Send Message. | Click
TS_11_TC_06 | To check the fuctionalities of My Messages module with Search. | 1.System must be working. | 1 | Enter URL. | https://www.bloodbanktoday.com | User should able to search message from my message. | After clicking on search message user can select the options like search message, replay type and priority then click on search message user will check the details of given input. | Passed
|  | 2. Internet must be available. | 2 | Click on Login Button. | Click
|  | 3. Web Browser must be working. | 3 | Enter Email ID or Mobile No. | Pradeep33reigns@gmail.com
|  | 4. URL must be working. | 4 | Enter Password. | loookli@123
|  | 5. My Messages button must be clickable. | 5 | Click on Sign In Button. | Click
|  |  | 6 | Click on My Message. | Click
|  |  | 7 | Select Search Message For. | Request
|  |  | 8 | Select Replay Type . | Done
|  |  | 9 | Select Priority type. | Early
|  |  | 10 | Enter Subject on search bar. | Important
|  |  | 11 | Click on Search Button. | Click
TS_12_TC_01 | To check the fuctionalities of Edit Profile module with Add Blood Donation Report. | 1.System must be working. | 1 | Enter URL. | https://www.bloodbanktoday.com | User should able to edit profile and also able to add blood donation report. | When user click on Add Blood Donation Report user should navigate on By Donation Report page in that if user fill out the fields like Donation Date, Slip No. if any, Reference Id if any, Receiver Mobile if any, Receiver Name if any andRelaton with if any.Then Click on submit button. System display message Data submit successfully. | Passed. | when user fill out the fields with invalid data like Receiver Mobile Number, entered more than 10 digits that data also taken. Shows data submit successfully. | Fuctional Defect
|  | 2. Internet must be available. | 2 | Click on Login Button. | Click
|  | 3. Web Browser must be working. | 3 | Enter Email ID or Mobile No. | Pradeep33reigns@gmail.com
|  | 4. URL must be working. | 4 | Enter Password. | loookli@123
|  | 5. Edit Profile button must be clickable. | 5 | Click on Sign In Button. | Click
|  |  | 6 | Click on Edit Profile button. | Click
|  |  | 7 | Click on Add Blood Donation Report button. | Click
TS_12_TC_02 | To check the fuctionalities of Edit Profile module with Copy Link. | 1.System must be working. | 1 | Enter URL. | https://www.bloodbanktoday.com | User should able to copy the link. | When user click on copy link button user should get a pop up message i.e. Link Copied. | Passed.
|  | 2. Internet must be available. | 2 | Click on Login Button. | Click
|  | 3. Web Browser must be working. | 3 | Enter Email ID or Mobile No. | Pradeep33reigns@gmail.com
|  | 4. URL must be working. | 4 | Enter Password. | loookli@123
|  | 5. Edit Profile button must be clickable. | 5 | Click on Sign In Button. | Click
|  |  | 6 | Click on Edit Profile button. | Click
|  |  | 7 | Click on Clopy link button. | Click
TS_12_TC_03 | To check the fuctionalities of Edit Profile module with Facebook share. | 1.System must be working. | 1 | Enter URL. | https://www.bloodbanktoday.com | User should able to click on Event button. | After Clicking on Edit profile button user should able to navigate on facebook share page. | Passed.
|  | 2. Internet must be available. | 2 | Click on Login button. | Click
|  | 3. Web Browser must be working. | 3 | Enter Email Id or Mobile No. | Pradeep33reigns@gmail.com
|  | 4. URL must be working. | 4 | Enter Password. | loookli@123
|  | 5. Edit Profile button must be clickable. | 5 | Click on Sign In | Click
|  |  | 6 | Click on Edit Profile button. | Click
|  |  | 7 | Click on Facebook share. | Click
TS_12_TC_04 | To check the fuctionalities of Edit Profile module with WhatsApp share. | 1.System must be working. | 1 | Enter URL. | https://www.bloodbanktoday.com | User should not able to click WhatsApp share Button. | After Clicking on Whatsapp button user should not able to navigate on WhatsApp share page button, and whatsApp share button is not working. | Failed. | User should not able to Invite our friends using WhatsApp share. WhatsApp share button is not working. | Fuctional Defect | When user click on WhatsApp share button, then that button is not working user still in edit profile page only. | Wrong Functional Defect.
|  | 2. Internet must be available. | 2 | Click on Login button. | Click
|  | 3. Web Browser must be working. | 3 | Enter Email Id or Mobile No. | Pradeep33reigns@gmail.com
|  | 4. URL must be working. | 4 | Enter Password. | loookli@123
|  | 5. Edit Profile button must be clickable. | 5 | Click on Sign In | Click
|  |  | 6 | Click on Edit Profile button. | Click
|  |  | 7 | Click on Whatsapp share. | Click
TS_12_TC_05 | To check the fuctionalities of Edit Profile module with Image. | 1.System must be working. | 1 | Enter URL. | https://www.bloodbanktoday.com | User should able to click on Image Button. | After clicking that image button user should able to choose file and upload image. | Passed.
|  | 2. Internet must be available. | 2 | Click on Login button. | Click
|  | 3. Web Browser must be working. | 3 | Enter Email Id or Mobile No. | Pradeep33reigns@gmail.com
|  | 4. URL must be working. | 4 | Enter Password. | loookli@123
|  | 5. Edit Profile button must be clickable. | 5 | Click on Sign In | Click
|  |  | 6 | Click on Edit Profile button. | Click
|  |  | 7 | Click on image button. | Click
TS_12_TC_06 | To check the fuctionalities of Edit Profile module with Edit button. | 1.System must be working. | 1 | Enter URL. | https://www.bloodbanktoday.com | User should able to click on Edit button. | After clicking on edit button user should able to edit basic information like Name, Gender, Show Mobile, SMS Alert, Donate Type, Weight in kg, Blood Group, D.O.B and About Myself and also to save or cancel the details. | Passed.
|  | 2. Internet must be available. | 2 | Click on Login button. | Click
|  | 3. Web Browser must be working. | 3 | Enter Email Id or Mobile No. | Pradeep33reigns@gmail.com
|  | 4. URL must be working. | 4 | Enter Password. | loookli@123
|  | 5. Edit Profile button must be clickable. | 5 | Click on Sign In | Click
|  |  | 6 | Click on Edit Profile button. | Click
|  |  | 7 | Click on edit button. | Click
TS_12_TC_07 | To check the fuctionalities of Edit Profile module with Address Information. | 1.System must be working. | 1 | Enter URL. | https://www.bloodbanktoday.com | User should able to edit the Address Information. | After clicking on edit button user should able to edit Address information like Select State, Select City ,Select Tehsil,Enter Near By,Pin Code,Enter Address,Select Occupation,Enter Detail nd also to save or cancel the details. | Passed. | User should able to edit the Address information but the Tehsil and occupation spelling is like Tehasil and Oqupation. | Non Fuctional Defect
|  | 2. Internet must be available. | 2 | Click on Login button. | Click
|  | 3. Web Browser must be working. | 3 | Enter Email Id or Mobile No. | Pradeep33reigns@gmail.com
|  | 4. URL must be working. | 4 | Enter Password. | loookli@123
|  | 5. Edit Profile button must be clickable. | 5 | Click on Sign In | Click
|  |  | 6 | Click on Edit Profile button. | Click
|  |  | 7 | Click on edit button from Address Information. | Click
|  |  | 8 | Select State. | TamilNadu
|  |  | 9 | Select City. | Coimbatore
|  |  | 10 | Select Tehasil. | Thondamuthur
|  |  | 11 | Enter Near By | Devarayapuram
|  |  | 12 | Pin Code | 641109
|  |  | 13 | Enter Address | 610/612 PN classes near rotomaker pvt ltd Devarayapuram , hyderbad 641109
|  |  | 14 | Select Occupation. | Reatil Banking
|  |  | 15 | Enter Detail | Jr Relationship Excetive
|  |  | 16 | Click on Save button. | Click
TS_12_TC_08 | To check the fuctionalities of Edit Profile module with Contact Information. | 1.System must be working. | 1 | Enter URL. | https://www.bloodbanktoday.com | User should able to edit Contact information like Mobile No. | After clicking on edit button user should able to edit Contact information like Mobile Number but OTP is not getthing of given number. | Partial Failed. | When user edit the Mobile number system display message Enter otp for Mobile Number Verify but user not getting any OTP. Then user click on If Not Get Message Click Resend button then that button is also not working. | Wrong Fuctional and Fuctional Defect. | When user edit the Mobile number system display message Enter otp for Mobile Number Verify but user not getting any OTP. Then user click on If Not Get Message Click Resend button then that button is also not working. | Wrong Functional Defect.
|  | 2. Internet must be available. | 2 | Click on Login button. | Click
|  | 3. Web Browser must be working. | 3 | Enter Email Id or Mobile No. | Pradeep33reigns@gmail.com
|  | 4. URL must be working. | 4 | Enter Password. | loookli@123
|  | 5. Edit Profile button must be clickable. | 5 | Click on Sign In | Click
|  |  | 6 | Click on Edit Profile button. | Click
|  |  | 7 | Click on edit button from Contact Information . | Click
|  |  | 8 | Enter Mobile No. | 7395835653
|  |  | 9 | Enter Email Id. | Pradeep33reigns@gmail.com
|  |  | 10 | Click on edit. | Click
TS_12_TC_09 | To check the fuctionalities of Edit Profile module with Edit Your Email ID. | 1.System must be working. | 1 | Enter URL. | https://www.bloodbanktoday.com | User should able to edit the Email Id. | After clicking on edit button user should able to edit the Email Id but user not getting any verification link. After click on send Email verify link system display message Data Successful Update. | Failed | After editing the Email Id when user click on send Email verify Link button system display message that Data Successfol Update and in that message successful spelling is incorrect as well as not getting any verification link. | Wrong Fuctional and Fuctional Defect. | After editing the Email Id user click on send Email verify Link button system display message that Data Successfully Update and user not getting any verification link. | Wrong Functional Defect.
|  | 2. Internet must be available. | 2 | Click on Login button. | Click
|  | 3. Web Browser must be working. | 3 | Enter Email Id or Mobile No. | Pradeep33reigns@gmail.com
|  | 4. URL must be working. | 4 | Enter Password. | loookli@123
|  | 5. Edit Profile button must be clickable. | 5 | Click on Sign In | Click
|  |  | 6 | Click on Edit Profile button. | Click
|  |  | 7 | Click on Edit Your Email Id. | Click
TS_12_TC_10 | To check the fuctionalities of Edit Profile module with Change Password. | 1.System must be working. | 1 | Enter URL. | https://www.bloodbanktoday.com | User should able to change the Password. | After clicking on edit button user should able to change Password and update the password. | Passed
|  | 2. Internet must be available. | 2 | Click on Login button. | Click
|  | 3. Web Browser must be working. | 3 | Enter Email Id or Mobile No. | Pradeep33reigns@gmail.com
|  | 4. URL must be working. | 4 | Enter Password. | loookli@123
|  | 5. Edit Profile button must be clickable. | 5 | Click on Sign In | Click
|  |  | 6 | Click on Edit Profile button. | Click
|  |  | 7 | Click on Edit from Change Password. | Click

## Defect Report
Defect Report.
Defect ID | Defect Reporting | Project Name | Project Version | Module Name | Type of Defect | Phase In Which Defects Is Identified | Summary Of Defect | Steps To Reproduce | Expected Result | Actual Result | Test Data | Description Of Defect | Severity | Priority | Status | Reported By | Reported To
ID_001 | 2023-06-28 | Blood Bank Today | 1.1 | Register | Wrong Functional Defect | System Testing | User is able to register with Valid data but OTP is not working. | Enter URL | User should able to do registration to do registration with Valid data. | User is able to register with Valid data but OTP is not working. Which is asking by the system for account verfication after clicking on Submit button. | https://bloodbanktoday.com/ | After clicking on submit button system is asking for OTP which user received on Dashboard rather than registered mobile number. | Major |  | New | Junior Tester. | Senior Tester.
[8 empty] | Click on Registration Button. |  |  | Click
[8 empty] | Enter Full Name |  |  | Pradeep
[8 empty] | Enter Email |  |  | Pradeep33reigns@gmail.com
[8 empty] | Enter Mobile Number |  |  | 7395835653
[8 empty] | Create Password |  |  | Pradeep@001
[8 empty] | Select BloodGroup |  |  | O+
[8 empty] | Select Gender |  |  | Male
[8 empty] | Select DOB |  |  | 2000-02-29
[8 empty] | Select Weight |  |  | 70
[8 empty] | Select Last Donation Date |  |  | 2023-11-03
[8 empty] | Select Yes/No for Show Mobile |  |  | Yes
[8 empty] | Select Yes/No for SMS Alert |  |  | Yes
[8 empty] | Enter Pin/Zip code |  |  | 641109
[8 empty] | Select State |  |  | TamilNadu
[8 empty] | Select District |  |  | Coimbatore
[8 empty] | Select Tehsil |  |  | Thondamuthur
[8 empty] | Enter City or Village |  |  | Devarayapuram
[8 empty] | Accept Terms & Conditions |  |  | Tick
[8 empty] | Click on Submit Buttom |  |  | Submit
[8 empty] | Enter OTP |  |  | OTP
ID_002 | 2023-06-28 | Blood Bank Today | 1.1 | Register | Wrong Functional Defect | System Testing | User should not able to registration with invalid. | Enter URL | User should not able to registration with invalid. | User is able to do registration with invalid data. | https://bloodbanktoday.com/ | Fields like Full Name City should accept alphabets but in actual it is taking alphanumeric , Email is taking with wrong domain, Mobile no taking more than 3 digit. | Major |  | New | Junior Tester. | Senior Tester.
[8 empty] | Click on Registration Button. |  |  | Click
[8 empty] | Enter Full Name |  |  | Pradeep 123
[8 empty] | Enter Email |  |  | Pradeep123@gmail.com
[8 empty] | Enter Mobile Number |  |  | 73958356537
[8 empty] | Create Password |  |  | loook
[8 empty] | Select BloodGroup |  |  | O+
[8 empty] | Select Gender |  |  | Male
[8 empty] | Select DOB |  |  | 2000-02-29
[8 empty] | Select Weight |  |  | 610
[8 empty] | Select Last Donation Date |  |  | 2023-11-03
[8 empty] | Select Yes/No for Show Mobile |  |  | Yes
[8 empty] | Select Yes/No for SMS Alert |  |  | Yes
[8 empty] | Enter Pin/Zip code |  |  | 6411095
[8 empty] | Select State |  |  | TamilNadu
[8 empty] | Select District |  |  | Coimbatore
[8 empty] | Select Tehsil |  |  | Thondamuthur
[8 empty] | Enter City or Village |  |  | Devarayapuram 123
[8 empty] | Accept Terms & Conditions |  |  | Tick
[8 empty] | Click on Submit Buttom |  |  | Submit
[8 empty] | Enter OTP |  |  | Wrong OTP
ID_003 | 2023-06-28 | Blood Bank Today | 1.1 | Register | Wrong Functional Defect | System Testing | User is able to do registration with Valid and Invalid data. | Enter URL | User should not able to do register with Valid & Invalid data. | User is able to do registration with Valid and Invalid data. | https://bloodbanktoday.com/ | User is able to do registration with Valid and Invalid data. | Major |  | New | Junior Tester. | Senior Tester.
[8 empty] | Click on Registration Button. |  |  | Click
[8 empty] | Enter Full Name |  |  | Pradeep
[8 empty] | Enter Email |  |  | Pradeep33reigns@gmail.comm
[8 empty] | Enter Mobile Number |  |  | 123456789
[8 empty] | Create Password |  |  | Pradeep@001
[8 empty] | Select BloodGroup |  |  | O+
[8 empty] | Select Gender |  |  | Male
[8 empty] | Select DOB |  |  | 2000-02-29
[8 empty] | Select Weight |  |  | 610
[8 empty] | Select Last Donation Date |  |  | 2023-11-03
[8 empty] | Select Yes/No for Show Mobile |  |  | Yes
[8 empty] | Select Yes/No for SMS Alert |  |  | Yes
[8 empty] | Enter Pin/Zip code |  |  | 6411095
[8 empty] | Select State |  |  | TamilNadu
[8 empty] | Select District |  |  | Coimbatore
[8 empty] | Select Tehsil |  |  | Thondamuthur
[8 empty] | Enter City or Village |  |  | Devarayapuram
[8 empty] | Accept Terms & Conditions |  |  | Tick
[8 empty] | Click on Submit Buttom |  |  | Submit
[8 empty] | Enter OTP |  |  | OTP
ID_004 | 2023-06-28 | Blood Bank Today | 1.1 | Register | Wrong Functional Defect | System Testing | User should not able to do registered with mandatory data. | Enter URL. | User should able to register with mandatory data. | User should not able to do registered with mandatory data. | https://bloodbanktoday.com/ | After inputing the mandatory data system asking for more details of the user. | Partial Failed |  | New | Junior Tester. | Senior Tester.
[8 empty] | Click on Registration Button. |  |  | Click
[8 empty] | Enter Full Name |  |  | Pradeep
[8 empty] | Select BloodGroup |  |  | O+
[8 empty] | Select Gender |  |  | Male
[8 empty] | Select Weight |  |  | 61
[8 empty] | Select Yes/No for SMS Alert |  |  | Yes
[8 empty] | Click on Submit Buttom |  |  | Click
[8 empty] | Enter OTP |  |  | OTP
ID_005 | 2023-03-07 | Blood Bank Today | 1.1 | Login | Wrong Functional Defect | System Testing | With the help of Member ID user should able to change the password. | Enter URL. | With the help of Member ID user should able to change the password. | User should not able to change the password with memberid. System asking for 10 digit of Member id which is not provided by system. | https://bloodbanktoday.com/ | After click on forgot your password button system asking to select any option for Recovery password. When user click on Member Id system asked enter Member ID but Member ID is not provided by system. | Major |  | New | Junior Tester. | Senior Tester.
[8 empty] | Click on Login Button. |  |  | Click
[8 empty] | Click on forgot your password |  |  | Click
[8 empty] | Enter Member ID |  |  | Member ID
[8 empty] | Click on Send message |  |  | Click
ID_006 | 2023-03-07 | Blood Bank Today | 1.1 | Login | Wrong Functional Defect | System Testing | With the help of Login ID user should able to change the password. | Enter URL. | With the help of Login ID user should able to change the password | User should not able to change the password with Login ID. System asking for 10 digit of Login IDwhich is not provided by system. | https://bloodbanktoday.com/ | After clicking on forgot your password system asking to select any option for Recovery password. When user click on Login ID system asked enter Login ID but Login ID is not provided by system. | Major |  | New | Junior Tester. | Senior Tester.
[8 empty] | Click on Login Button. |  |  | Click
[8 empty] | Click on forgot your password |  |  | Click
[8 empty] | Click on Login ID |  |  | Click
[8 empty] | Enter Login ID |  |  | Login ID
[8 empty] | Click on Send message |  |  | Click
ID_007 | 2023-03-07 | Blood Bank Today | 1.1 | Login | Wrong Functional Defect | System Testing | With the help of Email ID user should able to change the password. | Enter URL. | With the help of Email ID user should able to change the password. | User should not able to recover password with Email ID. | https://bloodbanktoday.com/ | After clicking on forgot your password system asked select any option for Recovery password. When user click on Email ID and input existing email Id then click on send Email button system display message with valid user Name, Mobile No. and Email id and then user click on send messge button after that system asked enter otp but user should not getting any otp on his registered Email id. | Major |  | New | Junior Tester. | Senior Tester.
[8 empty] | Click on Login Button. |  |  | Click
[8 empty] | Click on forgot your password |  |  | Click
[8 empty] | Click on Email ID |  |  | Click
[8 empty] | Enter Email ID |  |  | Pradeep33reigns@gmail.com
[8 empty] | Click on Send message |  |  | Click
ID_008 | 2023-03-07 | Blood Bank Today | 1.1 | Login | Wrong Functional Defect | System Testing | With the help of Mobile No user should able to change the password. | Enter URL. | With the help of Mobile No user should able to change the password. | User should not able to recover password with Mobile No. | https://bloodbanktoday.com/ | After clicking on forgot your password system asked select any option for Recovery password. When user entered a mobile no. system display message send verify code for You are(User name), mobile number and Email ID. Then user click on send message button system ask to Enter OTP but user not getting any OTP on registered mobile number which user receive on Dashboard. | Major |  | New | Junior Tester. | Senior Tester.
[8 empty] | Click on Login Button. |  |  | Click
[8 empty] | Click on forgot your password |  |  | Click
[8 empty] | Click on Mobile No |  |  | Click
[8 empty] | Enter Mobile No |  |  | 7395835653
[8 empty] | Click on Send message |  |  | Click
ID_009 | 2023-03-07 | Blood Bank Today | 1.1 | Login | Wrong Functional Defect | System Testing | Cursor should move to the facebook window, where user will enter sign in credentials. | Enter URL. | Cursor should move to the facebook window, where user will enter sign in credentials. | User should not able to Login with Facebook. | https://bloodbanktoday.com/ | When user click on sign in with facebook button so that button is not working. | Major |  | New | Junior Tester. | Senior Tester.
[8 empty] | Click on Login Button. |  |  | Click
[8 empty] | Click on Facebook |  |  | Click
ID_010 | 2023-03-07 | Blood Bank Today | 1.1 | Login | Wrong Functional Defect | System Testing | User should navigate to Registration Portal when clicked on Sign up now. | Enter URL. | User should navigate to Registration Portal when clicked on Sign up now. | User should able to do Login with Sign Up Now but OTP is not working. | https://bloodbanktoday.com/ | After clicking on signup button system is navigate to registration portal and user fill out all the details and click on submit button sytem asking for OTP which user received on Dashboard rather than registered mobile no. | Major |  | New | Junior Tester. | Senior Tester.
[8 empty] | Click on Login Button. |  |  | Click
[8 empty] | Click on Sign up now |  |  | Click
ID_011 | 2023-03-07 | Blood Bank Today | 1.1 | Find Blood | Wrong Functional Defect | System Testing | With only blood group, user should not find blood. user should receive error message i.e please select district. | Enter URL. | With only blood group, user should not find blood. user should receive error message i.e please select district. | User should not able to find blood with only blood group. | https://bloodbanktoday.com/ | When user is click on find blood button system asking for enter the blood group but after entering the blood group system asking for enter state, district and tehsil. | Minor |  | New | Junior Tester. | Senior Tester.
[8 empty] | Select Blood Group |  |  | O+
Select State
Select District
Select Tehsil
[8 empty] | Click on Find Blood |  |  | Click
ID_012 | 2023-03-07 | Blood Bank Today | 1.1 | Find Blood | Wrong Functional Defect | System Testing | With only blood group and state, user should not find blood. | Enter URL. | With only blood group and state, user should not find blood. | User should not able to find blood with only blood group and state. | https://bloodbanktoday.com/ | When user is click on blood group button and state button and inputing the details system asking for district and tehsil. | Minor |  | New | Junior Tester. | Senior Tester.
[8 empty] | Select Blood Group |  |  | O+
[8 empty] | Select State |  |  | TamilNadu
Select District
Select Tehsil
[8 empty] | Click on Find Blood |  |  | Click
ID_013 | 2023-03-07 | Blood Bank Today | 1.1 | Request Blood | Wrong Functional Defect | System Testing | User should able to request blood with vaild data. | Enter URL. | User should able to request blood with vaild data. | User is able to request blood with Valid data but OTP is not working. Which is asking by the system for account verfication after clicking on Submit button. | https://bloodbanktoday.com/ | After clicking on submit button system asking for OTP which user recevied on Dashboard rather than registered mobile number. | Major |  | New | Junior Tester. | Senior Tester.
[8 empty] | Click on Request Blood |  |  | Click
[8 empty] | Enter Patient Name |  |  | Pradeep
[8 empty] | Enter Doctor Name |  |  | Dr. Ajay Gaikwad
[8 empty] | Select Blood Group |  |  | O+
[8 empty] | Select State |  |  | TamilNadu
[8 empty] | Select District |  |  | Coimbatore
[8 empty] | Select Tehsil |  |  | Thondamuthur
[8 empty] | Enter Hospital Name and Address |  |  | Gold Care Hospital Sr no 101 /102 PN Classic , Devarayapuram Rd, Tilak Colony, TamilNadu 9th Block,TamilNadu ,Coimbatore,Thondamuthur 641109
[8 empty] | Enter Contact Name |  |  | Pradeep C
[8 empty] | Enter Mobile Number |  |  | 7395835653
[8 empty] | Enter Date when need |  |  | 6/30/2023
[8 empty] | Select Priorty |  |  | Early
[8 empty] | Enter Email |  |  | Pradeep123@gmail.com
[8 empty] | Enter other message |  |  | please help as soon as possible with blood
[8 empty] | Click Send Request |  |  | Click
ID_014 | 2023-03-07 | Blood Bank Today | 1.1 | Request Blood | Wrong Functional Defect | System Testing | User should not able to request blood with invaild data. | Enter URL. | User should not able to request blood with invaild data. | User is able to request blood with Invalid data | https://bloodbanktoday.com/ | Fields like Patient Name,Doctor name should accept alphabets but in actual it is taking alphanumeric , Email is taking with wrong domain, Mobile no taking more than 10 digit. | Major |  | New | Junior Tester. | Senior Tester.
[8 empty] | Click on Request Blood |  |  | Click
[8 empty] | Enter Patient Name |  |  | Pradeep76r
[8 empty] | Enter Doctor Name |  |  | Dr. Ajay Gaikwad855
[8 empty] | Select Blood Group |  |  | O+
[8 empty] | Select State |  |  | TamilNadu
[8 empty] | Select District |  |  | Coimbatore
[8 empty] | Select Tehsil |  |  | Thondamuthur
[8 empty] | Enter Hospital Name and Address |  |  | Gold Care Hospital Sr no 101 /102 PN Classic , Devarayapuram Rd, Tilak Colony, TamilNadu 9th Block,TamilNadu ,Coimbatore,Thondamuthur 641109
[8 empty] | Enter Contact Name |  |  | Pradeep C 423
[8 empty] | Enter Mobile Number |  |  | 70583112@g
[8 empty] | Enter Date when need |  |  | 6/30/2023
ID_015 | 2023-03-07 | Blood Bank Today | 1.1 | Request Blood | Wrong Functional Defect | System Testing | User should not able to Request Blood with Valid and Invalid data. | Enter URL. | User should not able to Request Blood with Valid and Invalid data. | User is able to do request blood with Valid and Invalid data. | https://bloodbanktoday.com/ | After Inputing valid and invalid data user can able to login and navigate to verfication Page. | Low |  | New | Junior Tester. | Senior Tester.
[8 empty] | Click on Request Blood |  |  | Click
[8 empty] | Enter Patient Name |  |  | Pradeep
[8 empty] | Enter Doctor Name |  |  | Dr. Ajay Gaikwad.
[8 empty] | Select Blood Group |  |  | O+
[8 empty] | Select State |  |  | TamilNadu
[8 empty] | Select District |  |  | Coimbatore
[8 empty] | Select Tehsil |  |  | Thondamuthur
[8 empty] | Enter Hospital Name and Address |  |  | Gold Care Hosp22ital Sr no 101 /102 PN Classic , Devarayapuram Rd, Tilak Colony, TamilNadu 9th Block,TamilNadu ,Coimbatore,Thondamuthur 641109
[8 empty] | Enter Contact Name |  |  | Pradeep C252
[8 empty] | Enter Mobile Number |  |  | 7824189810#
[8 empty] | Enter Date when need |  |  | 6/30/2023
[8 empty] | Select Priorty |  |  | Early
[8 empty] | Enter Email |  |  | Manutiwari09@gafmail.com
[8 empty] | Enter other message |  |  | please help as soon as possible with blood
[8 empty] | Click Send Request |  |  | Click
ID_016 | 2023-03-07 | Blood Bank Today | 1.1 | Request Blood | Wrong Functional Defect | System Testing | User should able to request blood with mandatory data. | Enter URL. | User should able to request blood with mandatory data. | User can able to request with mandatory data. | https://bloodbanktoday.com/ | After click on send request button system display message enter message code for mobile number verification but user not gettting any code. | Low |  | New | Junior Tester. | Senior Tester.
[8 empty] | Click on Request Blood |  |  | Click
[8 empty] | Enter Patient Name |  |  | Pradeep
[8 empty] | Enter Doctor Name |  |  | Dr. Ajay Gaikwad.
[8 empty] | Select Blood Group |  |  | O+
[8 empty] | Enter Hospital Name and Address |  |  | Gold Care Hospital Sr no 101 /102 PN Classic , Devarayapuram Rd, Tilak Colony, TamilNadu 9th Block,TamilNadu ,Coimbatore,Thondamuthur 641109
[8 empty] | Enter Contact Name |  |  | Pradeep C
[8 empty] | Enter Mobile Number |  |  | 7395835653
[8 empty] | Enter Date when need |  |  | 6/30/2023
[8 empty] | Select Priorty |  |  | Early
[8 empty] | Enter Email |  |  | Pradeep123@gmail.com
[8 empty] | Enter other message |  |  | please help as soon as possible with blood
[8 empty] | Click Send Request |  |  | Click
ID_017 | 2023-03-07 | Blood Bank Today | 1.1 | Blogs | Wrong Functional Defect | System Testing | User should able to click on that link i.e. By Blood Bank today. | Enter URL. | User should able to click on that link i.e. By Blood Bank today. | User should not able to get the details of By Blood Bank today link system shows error message. | https://bloodbanktoday.com/ | When user click on By Blood Bank today, it shows server error i.e. 404- File or Directory not found. | Major |  | New | Junior Tester. | Senior Tester.
[8 empty] | Click on Blogs |  |  | Click
[8 empty] | Click on Hyperlink By Blood Bank today |  |  | Click
ID_018 | 2023-03-07 | Blood Bank Today | 1.1 | Blogs | Wrong Functional Defect | System Testing | User should not able to click WhatsApp share Button. | Enter URL. | User should not able to click WhatsApp share Button. | After Clicking on Whatsapp button user should not able to navigate on WhatsApp share page button, and whatsApp share button is not working. | https://bloodbanktoday.com/ | When user click on WhatsApp share button, then that button is not working user still in Blogs page only. | Major |  | New | Junior Tester. | Senior Tester.
[8 empty] | Click on Blogs |  |  | Click
[8 empty] | Click on Whatsapp Share Button |  |  | Click
ID_019 | 2023-03-07 | Blood Bank Today | 1.1 | Blogs | Wrong Functional Defect | System Testing | User should not able to click on Web Solution Company Button. | Enter URL. | User should not able to click on Web Solution Company Button. | After clicking on Web Solution Company Hyperlink user should not able to Access the Hyperlink, because Hyperlink is not working. | https://bloodbanktoday.com/ | When user click on Web Solution Company Hyperlink button, then that button is not working user still in Blog page only. | Major |  | New | Junior Tester. | Senior Tester.
[8 empty] | Click on Blogs |  |  | Click
[8 empty] | Click on Web Solution Company Button. |  |  | Click
ID_020 | 2023-03-07 | Blood Bank Today | 1.1 | Blogs | Wrong Functional Defect | System Testing | User should able to click on Visit Button. | Enter URL. | User should able to click on Visit Button. | After clicking on Visit button user should not able to search given history on Web solution company. | https://bloodbanktoday.com/ | When user click on the visit icon user not getting any details of the mentioned link i.e. Web Solutions Company instead of that user should nevigate on the home page i.e. Blood Bank Today. | Major |  | New | Junior Tester. | Senior Tester.
[8 empty] | Click on Blogs |  |  | Click
[8 empty] | Click on Visit Button. |  |  | Click
ID_021 | 2023-03-07 | Blood Bank Today | 1.1 | Blogs | Wrong Functional Defect | System Testing | User should not able to click on Share Icon. | Enter URL. | User should not able to click on Share Icon. | After clicking on share icon of Web solution company user should not able to click on share icon because icon is not working. | https://bloodbanktoday.com/ | When user click on share icon of Web solution company button, then that button is not working user still in Blog page only. | Major |  | New | Junior Tester. | Senior Tester.
[8 empty] | Click on Blogs |  |  | Click
[8 empty] | Click on Share Icon. |  |  | Click
ID_022 | 2023-03-07 | Blood Bank Today | 1.1 | Causes | Wrong Functional Defect | System Testing | User should not able to click WhatsApp share Button. | Enter URL. | User should not able to click WhatsApp share Button. | After Clicking on Whatsapp button user should not able to navigate on WhatsApp share page button,and whatsApp share button is not working. | https://bloodbanktoday.com/ | When user click on WhatsApp share button, then that button is not working user still in causes page only. | Major |  | New | Junior Tester. | Senior Tester.
[8 empty] | Click on Causes |  |  | Click
[8 empty] | Click on Whatsapp Share |  |  | Click
ID_023 | 2023-03-07 | Blood Bank Today | 1.1 | Causes | Wrong Functional Defect | System Testing | User should not able to click on Visit Also. | Enter URL. | User should not able to click on Visit Also. | After Clicking no visit also user should not able to click on visit also. | https://bloodbanktoday.com/ | When user click on Visit also button, then that button is not working user still in causes page only. | Minor |  | New | Junior Tester. | Senior Tester.
[8 empty] | Click on Causes |  |  | Click
[8 empty] | Click on Visit Also |  |  | Click
ID_024 | 2023-03-07 | Blood Bank Today | 1.1 | Events | Wrong Functional Defect | System Testing | User should not able to click WhatsApp share Button. | Enter URL. | User should not able to click WhatsApp share Button. | After Clicking on Whatsapp button user should not able to navigate on WhatsApp share page button and whatsApp share button is not working. | https://bloodbanktoday.com/ | When user click on WhatsApp share button, then that button is not working user still in event page only. | Major |  | New | Junior Tester. | Senior Tester.
[8 empty] | Click on Events |  |  | Click
[8 empty] | Click on Whatsapp Share. |  |  | Click
ID_025 | 2023-03-07 | Blood Bank Today | 1.1 | Events | Wrong Functional Defect | System Testing | User should not able to click on Visit Also. | Enter URL. | User should not able to click on Visit Also. | After Clicking no visit also user should not able to click on visit also. | https://bloodbanktoday.com/ | When user click on Visit also button, then that button is not working user still in event page only. | Minor |  | New | Junior Tester. | Senior Tester.
[8 empty] | Click on Events |  |  | Click
[8 empty] | Click on Visit also. |  |  | Click
ID_026 | 2023-03-07 | Blood Bank Today | 1.1 | News | Wrong Functional Defect | System Testing | User should not able to click WhatsApp share Button. | Enter URL. | User should not able to click WhatsApp share Button. | After Clicking on Whatsapp button user should not able to navigate on WhatsApp share page button and whatsApp share button is not working. | https://bloodbanktoday.com/ | When user click on WhatsApp share button, then that button is not working user still in News page only. | Major |  | New | Junior Tester. | Senior Tester.
[8 empty] | Click on News |  |  | Click
[8 empty] | Click on Whatsapp Share |  |  | Click
ID_027 | 2023-03-07 | Blood Bank Today | 1.1 | News | Wrong Functional Defect | System Testing | User should not able to click on Visit Also. | Enter URL. | User should not able to click on Visit Also. | After Clicking no visit also user should not able to click on visit also. | https://bloodbanktoday.com/ | When user click on Visit also button, then that button is not working user still in News page only. | Minor |  | New | Junior Tester. | Senior Tester.
[8 empty] | Click on News |  |  | Click
[8 empty] | Click on Visit Also |  |  | Click
ID_028 | 2023-03-07 | Blood Bank Today | 1.1 | Donate Us | Wrong Functional Defect | System Testing | User should not able to Donate Amount Manually. | Enter URL. | User should not able to Donate Amount Manually. | After Clicking no donate us button user should not able to Donate Amount Manually. | https://bloodbanktoday.com/ | After filling the details and user enter the amount of 700 and click on donate now button but system not allowing of pay manual amount its navigate too system page. | Minor |  | New | Junior Tester. | Senior Tester.
[8 empty] | Click on Donate Us |  |  | Click
[8 empty] | Enter Amount Manually. |  |  | 700
ID_029 | 2023-03-07 | Blood Bank Today | 1.1 | Donate Us | Wrong Functional Defect | System Testing | User should not able to donate money with Valid and Invalid data. | Enter URL. | User should not able to donate money with Valid and Invalid data. | User should not able to donate money with valid and Invalid data, user navigate on Choose a payment option page. | https://bloodbanktoday.com/ | When user enter invalid data for Full Name, Email, Country, State, City, Adress and Valid data for Mobile No, Pin/Zip code, user should able to donate money but system navigate on Choose a payment option page. | Major |  | New | Junior Tester. | Senior Tester.
[8 empty] | Click on Donate Us. |  |  | Click
[8 empty] | Select Amount |  |  | 100
[8 empty] | Enter Full Name. |  |  | Pradeep
[8 empty] | Enter Email. |  |  | Padeep345@gmail.com
[8 empty] | Enter Mobile No. |  |  | 7395835653452
[8 empty] | Enter Country. |  |  | India
[8 empty] | Enter State. |  |  | TamilNadu
[8 empty] | Enter City. |  |  | Coimbatore
[8 empty] | Enter Pin/Zip Code. |  |  | 641109
[8 empty] | Enter Address. |  |  | Gold Care Hospital Sr no 101 /102 PN Classic , Devarayapuram Rd, Tilak Colony, TamilNadu 9th Block,TamilNadu ,Coimbatore,Thondamuthur 641109
[8 empty] | Select Name in list. |  |  | Display
ID_030 | 2023-03-07 | Blood Bank Today | 1.1 | Edit Profile | Wrong Functional Defect | System Testing | User should not able to click WhatsApp share Button. | Enter URL. | User should not able to click WhatsApp share Button. | After Clicking on Whatsapp button user should not able to navigate on WhatsApp share page button, and whatsApp share button is not working. | https://www.bloodbanktoday.com | When user click on WhatsApp share button, then that button is not working user still in edit profile page only. | Major |  | New | Junior Tester. | Senior Tester.
[8 empty] | Click on Login button. |  |  | Click
[8 empty] | Enter Email Id or Mobile No. |  |  | Pradeep33reigns@gmail.com
[8 empty] | Enter Password. |  |  | loookli@123
[8 empty] | Click on Sign In |  |  | Click
[8 empty] | Click on Edit Profile button. |  |  | Click
[8 empty] | Click on Whatsapp share. |  |  | Click
ID_031 | 2023-03-07 | Blood Bank Today | 1.1 | Edit Profile | Wrong Functional Defect | System Testing | User should able to edit Contact information like Mobile No. | Enter URL. | User should able to edit Contact information like Mobile No. | After clicking on edit button user should able to edit Contact information like Mobile Number but OTP is not getthing of given number. | https://www.bloodbanktoday.com |  | Major |  | New | Junior Tester. | Junior Tester.
[8 empty] | Click on Login button. |  |  | Click
[8 empty] | Enter Email Id or Mobile No. |  |  | Pradeep33reigns@gmail.com
[8 empty] | Enter Password. |  |  | loookli@123
[8 empty] | Click on Sign In |  |  | Click
[8 empty] | Click on Edit Profile button. |  |  | Click
[8 empty] | Click on edit button from Contact Information . |  |  | Click
[8 empty] | Enter Mobile No. |  |  | 7395835653
[8 empty] | Enter Email Id. |  |  | Pradeep33reigns@gmail.com
[8 empty] | Click on edit. |  |  | Click
ID_032 | 2023-03-07 | Blood Bank Today | 1.1 | Edit Profile | Wrong Functional Defect | System Testing | User should able to edit the Email Id. | Enter URL. | User should able to edit the Email Id. | After clicking on edit button user should able to edit the Email Id but user not getting any verification link. After click on send Email verify link system display message Data | https://www.bloodbanktoday.com | After editing the Email Id user click on send Email verify Link button system display message that Data Successfully Update and user not getting any verification link. | Major |  | New | Junior Tester. | Senior Tester.
[8 empty] | Click on Login button. |  |  | Click
[8 empty] | Enter Email Id or Mobile No. |  |  | Pradeep33reigns@gmail.com
[8 empty] | Enter Password. |  |  | loookli@123
[8 empty] | Click on Sign In |  |  | Click
[8 empty] | Click on Edit Profile button. |  |  | Click
[8 empty] | Click on Edit Your Email Id. |  |  | Click